## Register
HVMC Comprehensive Risk Register — v2
Consolidates assessment (5×5), evaluation (weighted), mitigation (treatment, residual) and monitoring (KRIs). Weights in cells AB3:AE3.
[27 empty] | 19% | 36% | 33% | 12%
ID | Risk | Asset | Threat | Vulnerability | Owner | L | I (5×5) | 5×5 score | 5×5 rating | F | O | C | R | Weighted impact | Weighted score | Rating (weighted) | Strategy | Treatments | Live KRIs | Target residual | Target rating | Status | Opened | Last reviewed | Next review | ALE (if quantified)
R01 | Security incident goes undetected for months (no central logging or alerting) | All Azure resources | External attacker / insider (T1562.008 Disable Cloud Logs) | V01: 0 Log Analytics workspaces, 0 activity-log diagnostic settings, 0 alert rules, 0 NSG flow logs | Fatima Ali | 4 | 5 |  |  | 5 | 3 | 5 | 4 |  |  |  | Mitigate | C01 | K07 Red, K08 Red, K09 Amber | 6.66 | Medium | Treatment planned | 2026-10-13 | 2026-10-14 |  | 864926.46
R02 | ePHI exfiltration from EHR storage over the public internet | hvmcehrstorage (ePHI) | External attacker using stolen key or SAS token (T1530 Data from Cloud Storage) | V02: public network access Enabled, firewall default Allow, shared-key access enabled | Fatima Ali | 3 | 5 |  |  | 5 | 2 | 5 | 5 |  |  |  | Mitigate + Transfer | C02, T01 | K01 Red, K02 Amber | 3.92 | Low | Treatment planned | 2026-10-13 | 2026-10-14 |  | 600643.375
R03 | Lateral movement from Web tier to Data tier | HVMC-Data-Subnet (SQL 1433) | Attacker on compromised web server (T1021 Remote Services) | V03: HVMC-Data-NSG has no deny rule; default AllowVnetInBound (65000) permits Web→Data on any port | Fatima Ali | 3 | 5 |  |  | 5 | 4 | 5 | 4 |  |  |  | Mitigate | C03 | K05 Red | 4.52 | Low | Treatment planned | 2026-10-13 | 2026-10-14
R04 | Loss or takeover of the only Global Administrator account | Entra ID tenant | Phishing / account lockout (T1078.004 Valid Cloud Accounts) | V04: 1 Global Administrator, no break-glass account, same person is subscription Owner | Sabitha S Karanavar | 3 | 4 |  |  | 3 | 4 | 3 | 2 |  |  |  | Mitigate | C04 | K06 Red | 3.24 | Low | Treatment planned | 2026-10-13 | 2026-10-14
R05 | Ransomware or malicious deletion destroys EHR data | hvmcehrstorage (ePHI) | Ransomware group (T1486 Data Encrypted for Impact, T1485 Data Destruction) | V05: blob versioning off, soft delete only 7 days, 0 resource locks, restore never tested | Fatima Ali | 3 | 5 |  |  | 5 | 5 | 4 | 5 |  |  |  | Mitigate + Transfer | C05, T01 | K03 Red, K04 Amber | 9 | Medium | Treatment planned | 2026-10-13 | 2026-10-14 |  | 1057132.34
R06 | Contractor retains access after engagement ends; no BAA | VPN Portal | Trusted third party (T1078 Valid Accounts) | V06: Carlos Diaz account has no expiry date; no business associate agreement on file | Kevin O'Brien | 2 | 4 |  |  | 2 | 1 | 4 | 2 |  |  |  | Transfer | C12 | manual | 1.97 | Low | Treatment planned | 2026-10-13 | 2026-10-14
R07 | Shared test account in production can read ePHI | hvmcehrstorage (ePHI) | Insider or attacker reusing test credentials (T1078) | V07: Test Nurse - EHR holds HVMC-Nurse-EHR-ReadOnly on hvmcehrstorage | Sabitha S Karanavar | 2 | 3 |  |  | 1 | 1 | 3 | 2 |  |  |  | Avoid | C14 | K14 Amber | 0 | Eliminated | Treatment planned | 2026-10-13 | 2026-10-14
R08 | Consent phishing or rogue app via open tenant settings | Entra ID tenant | External attacker (T1528 Steal Application Access Token) | V08: any user can register apps and create tenants; guest invites allowed from everyone | Sabitha S Karanavar | 3 | 4 |  |  | 3 | 2 | 4 | 3 |  |  |  | Mitigate | C08 | K12 Amber, K13 Amber | 2.97 | Low | Treatment planned | 2026-10-13 | 2026-10-14
R09 | Remote code execution via OpenSSH 6.6.1p1 (CVE-2023-38408, CVSS 9.8) | Legacy public server (scanme.nmap.org lab target) | External attacker (T1190 Exploit Public-Facing Application) | V09: decade-old OpenSSH with ssh-agent forwarding flaw | Kevin O'Brien | 3 | 5 |  |  | 4 | 3 | 3 | 3 |  |  |  | Avoid | C13 | manual | 0 | Eliminated | Treatment planned | 2026-09-08 | 2026-10-14
R10 | Remote code execution via Apache 2.4.7 mod_lua (CVE-2021-44790, CVSS 9.8) | Legacy public server (scanme.nmap.org lab target) | External attacker (T1190) | V10: Apache 2.4.7 with public exploits available | Kevin O'Brien | 4 | 5 |  |  | 4 | 3 | 3 | 3 |  |  |  | Avoid | C13 | manual | 0 | Eliminated | Treatment planned | 2026-09-08 | 2026-10-14
R11 | Malware uploaded to EHR storage is not detected | hvmcehrstorage (ePHI) | External attacker / infected workstation (T1105 Ingress Tool Transfer) | V11: all Defender for Cloud workload plans on Free tier; 0 security contacts configured | Denise Coleman | 3 | 4 |  |  | 3 | 4 | 3 | 3 |  |  |  | Mitigate | C06 | K10 Amber, K11 Amber | 5.28 | Low | Treatment planned | 2026-10-13 | 2026-10-14
R12 | Clinician credentials stolen by MFA-bypass (AiTM) phishing | EHR access (Doctors/Nursing groups) | Phishing operator (T1566 Phishing, T1557 Adversary-in-the-Middle) | V12: security defaults allow push/OTP MFA; no Conditional Access or phishing-resistant MFA | Denise Coleman | 3 | 4 |  |  | 3 | 2 | 4 | 3 |  |  |  | Mitigate | C07 | manual | 2.97 | Low | Treatment planned | 2026-10-13 | 2026-10-14 |  | 168180.145
R13 | Workforce member views patient records without a care need (snooping) | EHR (12 clinical users with RW) | Curious or malicious insider | V13: no record-level access auditing or monthly access-log review | Denise Coleman | 3 | 4 |  |  | 2 | 1 | 4 | 4 |  |  |  | Mitigate | C09 | manual | 4.84 | Low | Treatment planned | 2026-10-13 | 2026-10-14 |  | 74960.2932
R14 | Workforce violations go unpunished; training not tracked | Workforce | Negligent insider | V14: no sanction policy; HIPAA training completion not recorded | Daniel Osei | 2 | 4 |  |  | 2 | 1 | 3 | 2 |  |  |  | Mitigate | C10 | manual | 1.97 | Low | Treatment planned | 2026-10-13 | 2026-10-14
R15 | Accidental deletion of production network or storage | HVMC-CloudSecurity-RG | Administrator error | V15: 0 resource locks on the production resource group | Kevin O'Brien | 2 | 4 |  |  | 3 | 4 | 2 | 2 |  |  |  | Accept | A01 | K15 Amber | 5.82 | Low | Treatment planned | 2026-10-13 | 2026-10-14
R16 | Breach notification deadline missed (no Privacy Officer) | Regulatory compliance | Process failure | V16: Privacy Officer role vacant | Denise Coleman | 2 | 4 |  |  | 3 | 1 | 5 | 4 |  |  |  | Mitigate | C11 | manual | 2.73 | Low | Treatment planned | 2026-10-13 | 2026-10-14

## History
Risk register history — append-only
Every new risk, re-score, treatment and status change. Never edit past rows; add new ones.
Date | Risk | Event | Old value | New value | Changed by | Reason / evidence
2026-09-08 | R09 | Opened |  | Critical (legacy) | Sabitha S Karanavar | Identified in Apply Vulnerability Assessment Techniques scan; rated with Sept impact-floor method
2026-09-08 | R10 | Opened |  | Critical (legacy) | Sabitha S Karanavar | Identified in Apply Vulnerability Assessment Techniques scan; rated with Sept impact-floor method
2026-10-13 | R01 | Opened |  | 20 | Sabitha S Karanavar | HIPAA matrix gap G1 (audit controls)
2026-10-13 | R02 | Opened |  | 15 | Sabitha S Karanavar | HIPAA matrix gap G2 (storage public access)
2026-10-13 | R03 | Opened |  | 15 | Sabitha S Karanavar | HIPAA matrix gap G3 (Data NSG)
2026-10-13 | R04 | Opened |  | 12 | Sabitha S Karanavar | HIPAA matrix gap G4 (single Global Admin)
2026-10-13 | R05 | Opened |  | 8 | Sabitha S Karanavar | HIPAA matrix gap G8 (versioning off, DR untested)
2026-10-13 | R05 | Re-scored | 8 | 15 | Anthony Ruiz | Threat assessment: ransomware is the leading healthcare threat (L2→3) and EHR loss is patient-safety impact (I4→5).
2026-10-13 | R06 | Opened |  | 8 | Sabitha S Karanavar | HIPAA matrix gap G6 (contractor)
2026-10-13 | R07 | Opened |  | 6 | Sabitha S Karanavar | HIPAA matrix gap G7 (test account)
2026-10-13 | R08 | Opened |  | 12 | Anthony Ruiz | CIS checklist: open app registration and guest invites
2026-10-13 | R09 | Re-scored | Critical (legacy) | 15 | Anthony Ruiz | Converted to HVMC 5×5 scale (L3×I5). Likelihood Medium → 3.
2026-10-13 | R10 | Re-scored | Critical (legacy) | 20 | Anthony Ruiz | Converted to HVMC 5×5 scale (L4×I5). Public exploit code raises likelihood to 4.
2026-10-13 | R11 | Opened |  | 12 | Anthony Ruiz | CIS checklist: Defender plans Free, no security contact
2026-10-13 | R12 | Opened |  | 12 | Anthony Ruiz | Brainstorming + SWOT: AiTM phishing of clinicians
2026-10-13 | R13 | Opened |  | 12 | Anthony Ruiz | Brainstorming: insider snooping on patient records
2026-10-13 | R14 | Opened |  | 8 | Sabitha S Karanavar | HIPAA matrix gap G5 (sanction policy)
2026-10-13 | R15 | Opened |  | 8 | Anthony Ruiz | CIS checklist: no resource locks
2026-10-13 | R16 | Opened |  | 8 | Anthony Ruiz | Brainstorming + SWOT: Privacy Officer vacancy
2026-10-14 | R01 | Re-scored (method change) | 20 Critical (5×5) | 16.64 High (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R01 | Treatment assigned | Open | Mitigate: C01 | Denise Coleman | Risk Mitigation Planning; target residual 6.66 Medium
2026-10-14 | R01 | Monitoring baseline | — | K07 Red; K08 Red; K09 Amber | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R02 | Re-scored (method change) | 15 High (5×5) | 11.76 High (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R02 | Treatment assigned | Open | Mitigate + Transfer: C02, T01 | Denise Coleman | Risk Mitigation Planning; target residual 3.92 Low
2026-10-14 | R02 | Monitoring baseline | — | K01 Red; K02 Amber | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R03 | Re-scored (method change) | 15 High (5×5) | 13.56 High (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R03 | Treatment assigned | Open | Mitigate: C03 | Denise Coleman | Risk Mitigation Planning; target residual 4.52 Low
2026-10-14 | R03 | Monitoring baseline | — | K05 Red | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R04 | Re-scored (method change) | 12 High (5×5) | 9.72 Medium (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R04 | Treatment assigned | Open | Mitigate: C04 | Denise Coleman | Risk Mitigation Planning; target residual 3.24 Low
2026-10-14 | R04 | Monitoring baseline | — | K06 Red | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R05 | Re-scored (method change) | 15 High (5×5) | 14.01 High (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R05 | Treatment assigned | Open | Mitigate + Transfer: C05, T01 | Denise Coleman | Risk Mitigation Planning; target residual 9.00 Medium
2026-10-14 | R05 | Monitoring baseline | — | K03 Red; K04 Amber | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R06 | Re-scored (method change) | 8 Medium (5×5) | 4.60 Low (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R06 | Treatment assigned | Open | Transfer: C12 | Denise Coleman | Risk Mitigation Planning; target residual 1.97 Low
2026-10-14 | R07 | Re-scored (method change) | 6 Medium (5×5) | 3.56 Low (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R07 | Treatment assigned | Open | Avoid: C14 | Denise Coleman | Risk Mitigation Planning; target residual 0.00 Eliminated
2026-10-14 | R07 | Monitoring baseline | — | K14 Amber | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R08 | Re-scored (method change) | 12 High (5×5) | 8.91 Medium (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R08 | Treatment assigned | Open | Mitigate: C08 | Denise Coleman | Risk Mitigation Planning; target residual 2.97 Low
2026-10-14 | R08 | Monitoring baseline | — | K12 Amber; K13 Amber | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R09 | Re-scored (method change) | 15 High (5×5) | 9.57 Medium (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R09 | Treatment assigned | Open | Avoid: C13 | Denise Coleman | Risk Mitigation Planning; target residual 0.00 Eliminated
2026-10-14 | R10 | Re-scored (method change) | 20 Critical (5×5) | 12.76 High (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R10 | Treatment assigned | Open | Avoid: C13 | Denise Coleman | Risk Mitigation Planning; target residual 0.00 Eliminated
2026-10-14 | R11 | Re-scored (method change) | 12 High (5×5) | 10.08 Medium (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R11 | Treatment assigned | Open | Mitigate: C06 | Denise Coleman | Risk Mitigation Planning; target residual 5.28 Low
2026-10-14 | R11 | Monitoring baseline | — | K10 Amber; K11 Amber | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R12 | Re-scored (method change) | 12 High (5×5) | 8.91 Medium (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R12 | Treatment assigned | Open | Mitigate: C07 | Denise Coleman | Risk Mitigation Planning; target residual 2.97 Low
2026-10-14 | R13 | Re-scored (method change) | 12 High (5×5) | 7.62 Medium (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R13 | Treatment assigned | Open | Mitigate: C09 | Denise Coleman | Risk Mitigation Planning; target residual 4.84 Low
2026-10-14 | R14 | Re-scored (method change) | 8 Medium (5×5) | 3.94 Low (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R14 | Treatment assigned | Open | Mitigate: C10 | Denise Coleman | Risk Mitigation Planning; target residual 1.97 Low
2026-10-14 | R15 | Re-scored (method change) | 8 Medium (5×5) | 5.82 Low (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R15 | Treatment assigned | Open | Accept: A01 | Denise Coleman | Risk Mitigation Planning; target residual 5.82 Low
2026-10-14 | R15 | Monitoring baseline | — | K15 Amber | Anthony Ruiz | First automated KRI run (kri_monitor.py)
2026-10-14 | R16 | Re-scored (method change) | 8 Medium (5×5) | 6.12 Medium (weighted) | Denise Coleman | Adopted multi-criteria weighted model approved in Risk Evaluation Methods v1.0
2026-10-14 | R16 | Treatment assigned | Open | Mitigate: C11 | Denise Coleman | Risk Mitigation Planning; target residual 2.73 Low

## Monthly Snapshots
Register snapshots for trend tracking
One row per month-end (plus key events). Rows marked Target are plan values, not actuals.
Date | Type | Risks | Critical | High | Medium | Low | Eliminated | Total score | ALE top 5 | KRIs Red | KRIs Amber | KRIs Green | Note
2026-09-08 | Actual | 2 | 2 | 0 | 0 | 0 | 0 | [5 empty] | Vulnerability scan: R09, R10 (legacy Critical rating)
2026-10-13 | Actual | 16 | 2 | 9 | 5 | 0 | 0 | 198 | 2765842.6132 |  |  |  | Register created (5×5 scale)
2026-10-14 | Actual | 16 | 0 | 5 | 7 | 4 | 0 | 147.6 | 2765842.6132 | 6 | 9 | 0 | Weighted model adopted; first automated KRI run
2026-11-30 | Target | 16 | 0 | 1 |  |  | 3 |  | 1100000 | 2 |  |  | After Phase 1 + most of Phase 2
2026-12-13 | Target | 16 | 0 | 0 | 2 | 11 | 3 | 55.9 | 817836.0194 | 0 | 2 | 13 | Mitigation plan complete

## KRI Log
Automated KRI log
Appended by continuous_monitor.py runs
Run (UTC) | KRI | Indicator | Value | Target | Status | Risk | Control
2026-10-14T18:46:00Z | K01 | EHR storage public network access | Enabled | Disabled | Red | R02 | C02
2026-10-14T18:46:00Z | K02 | EHR storage shared-key access | True | false | Amber | R02 | C02
2026-10-14T18:46:00Z | K03 | EHR blob versioning | Disabled | Enabled | Red | R05 | C05
2026-10-14T18:46:00Z | K04 | Blob soft-delete retention (days) | 7 | ≥ 30 | Amber | R05 | C05
2026-10-14T18:46:00Z | K05 | Data-tier explicit deny rule | Missing | Present | Red | R03 | C03
2026-10-14T18:46:00Z | K06 | Global Administrators | 1 | 2–4 incl. break-glass | Red | R04 | C04
2026-10-14T18:46:00Z | K07 | Activity log exported to Log Analytics | 0 | ≥ 1 | Red | R01 | C01
2026-10-14T18:46:00Z | K08 | Activity-log alert rules | 0 | ≥ 3 | Red | R01 | C01
2026-10-14T18:46:00Z | K09 | Network flow logs | 0 | ≥ 1 | Amber | R01 | C01
2026-10-14T18:46:00Z | K10 | Defender for Storage | Free | Standard | Amber | R11 | C06
2026-10-14T18:46:00Z | K11 | Security alert contacts | 0 | ≥ 1 | Amber | R11 | C06
2026-10-14T18:46:00Z | K12 | Users can register applications | True | false | Amber | R08 | C08
2026-10-14T18:46:00Z | K13 | Guest invitations allowed from | everyone | adminsAndGuestInviters | Amber | R08 | C08
2026-10-14T18:46:00Z | K14 | Test/shared accounts in production | 1 | 0 | Amber | R07 | C14
2026-10-14T18:46:00Z | K15 | Resource locks on production RG | 0 | ≥ 1 (accepted risk) | Amber | R15 | A01

## Change Detection Log
Environmental change detection log
change_detector.py results; each change must be reconciled with a ticket (IP-1/IP-2/IP-3)
Run (UTC) | Baseline | Severity | Category | Change | Re-assess risks | Procedure | Ticket / reconciliation | Closed
2026-10-14T18-45-21Z | — | Info | all | Baseline snapshot: resources 12, nsg_rules 3, role_assignments 2, directory_roles 1, users 32, group_members 10, storage_security 6, public_ips 3, tenant_policy 6 | — | — | n/a
2026-10-14T18-46-10Z | 2026-10-14T18-45-21Z.json | Info | all | No changes since baseline | — | — | n/a

## Monitoring Runs
Continuous monitoring run history (monitoring_log.jsonl)
One row per scheduled run; Alert = Red KRI or High/Critical change
Run (UTC) | KRI Red | KRI Amber | KRI Green | Changes High+ | Changes total | KEV hits | Alert
2026-10-14T18:46:24Z | 6 | 9 | 0 | 0 | 0 | 0 | YES