## Board
Sabitha's Project Board
Healthcare IAM Operations Home Lab — 12-Week Daily Task Breakdown (No Subitems — Description & Deliverable in Update Text)
Week 1 — Scope Definition and First Build Steps (Aug 17 – Aug 20)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Define Organization Scenario and Scope |  | Sabitha S Karanavar | Description: Define the fictional hospital's name, confirm 30 employees, list departments and roles, write a one-paragraph project scope statement, and note what's out of scope (no custom app, no real hybrid sync). ¦ Deliverable: One-page scenario write-up + department list. |  |  |  | Sabitha S Karanavar | 12800000173
Research on core concepts of IAM and the Tech Stack |  | Sabitha S Karanavar |  |  |  |  | Sabitha S Karanavar | 12800000346
Research Why IAM Matters in Healthcare |  | Sabitha S Karanavar |  |  |  |  | Sabitha S Karanavar | 12800000519
Research on How to set up install Virtual Machine |  | Sabitha S Karanavar |  |  |  |  | Sabitha S Karanavar | 12800000692
[Security Rubric] Create Network Topology Diagram (LAN) |  | Sabitha S Karanavar | Description: Rubric — Network Security: Understand and Implement Network Topologies. Diagram the home-lab LAN topology (host machine, Server VM, Client VM, virtual switch/NAT network) using diagrams.net or similar, showing IP addressing. Write a short explanation of how this LAN topology supports secure communication and centralized network management via the domain controller. ¦ Deliverable: Network topology diagram (1 config: LAN) + 1/2-page explanation. |  |  |  | Sabitha S Karanavar
[Security Rubric] Secure Wireless Network (WPA2/WPA3 + WIPS) |  | Sabitha S Karanavar | Description: Rubric — Network Security: Secure Wireless Networks. Configure WPA2 or WPA3 security on your home Wi-Fi router (or a simulated AP in Packet Tracer/GNS3 if a physical router isn't available) for 1 network, and document a Wireless Intrusion Prevention System (WIPS) approach — enable a router's built-in rogue-AP/WIPS feature, or set up Kismet to detect unauthorized wireless access. This one is independent of the VM build, so it's a good task to knock out early. ¦ Deliverable: WPA2/WPA3 configuration screenshot + WIPS documentation. |  |  |  | Sabitha S Karanavar
Week 1 Status Update | [6 empty] | Sabitha S Karanavar | 12800000865
0/4
Week 2 — Domain Controller and Client (Aug 24 – Aug 27)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Set Up VirtualBox and Server VM Shell |  | Sabitha S Karanavar | Description: Install VirtualBox, download the Windows Server ISO, create the Server VM shell, and configure RAM/CPU/disk. ¦ Deliverable: Bootable Server VM (screenshot).
Install Windows Server OS |  | Sabitha S Karanavar | Description: Install the OS, set the hostname, configure a static IP, and verify network connectivity. ¦ Deliverable: Windows Server installed and reachable on the lab network (screenshot).
Build RBAC Skeleton and Simulated Application List |  | Sabitha S Karanavar | Description: For each department, define its simulated application (shared folder + future Entra app pairing), sketch the OU structure, and decide the security group naming convention. ¦ Deliverable: RBAC matrix v1 (role -> app -> access level) + OU sketch.
Promote to Domain Controller |  | Sabitha S Karanavar | Description: Install the AD DS role, run the promotion wizard, create the domain, and verify DNS. ¦ Deliverable: Functioning domain controller (dcdiag screenshot). |  |  |  | Sabitha S Karanavar | 12800001038
[Security Rubric] Map OSI/TCP-IP Models, Subnet the Lab, Diagram Secure Architecture |  | Sabitha S Karanavar | Description: Rubric — Network Security: Design Network Protocols and Architectures. Create a network diagram mapping the OSI 7-layer model and TCP/IP 4-layer model to the Server VM's traffic (e.g., AD DS communication) for 1 device, calculate and document proper subnetting for the lab's subnet (network/broadcast address, usable host range, mask), and extend the diagram into a secure network architecture that labels where security protocols apply (Kerberos for AD auth, LDAPS, SMB signing, TLS). ¦ Deliverable: OSI/TCP-IP + subnetting diagram + secure-architecture protocol map. |  |  |  | Sabitha S Karanavar
[Security Rubric] Set Up Kali/Parrot Security Testing VM |  | Sabitha S Karanavar | Description: Prep for the Network Security Tools, Vulnerability Assessment, and Cyber Threat Analysis rubric items coming later this week and in Weeks 3-4. Install Kali Linux or Parrot OS in VirtualBox on the same lab network segment as the Server VM and verify connectivity (ping / Nmap ping sweep). Install/update Wireshark, Nmap, a vulnerability scanner (OpenVAS or Nessus Essentials), Metasploit Framework, and the Social-Engineering Toolkit (SET). ¦ Deliverable: Running Kali/Parrot VM with tool versions confirmed + successful ping/scan reaching the Server VM (screenshot). |  |  |  | Sabitha S Karanavar
[Security Rubric] Implement Firewall Rule, IDS, and IPS with 1 Detected Event |  | Sabitha S Karanavar | Description: Rubric — Network Security: Implement Network Security Fundamentals. Configure 1 Windows Firewall (or pfSense, if you add a virtual firewall VM) rule restricting a specific port/app on the Server VM, install and configure Suricata or Snort as an IDS in detection mode, and configure IPS/blocking mode for 1 rule. Generate 1 example detected event by running an Nmap scan or a burst of failed RDP logins from the Kali VM you just built, and capture the alert. ¦ Deliverable: Firewall rule screenshot + IDS config + IPS config + 1 detected-event log/alert screenshot. |  |  |  | Sabitha S Karanavar
Week 2 Status Update | [6 empty] | Sabitha S Karanavar | 12800001730
0/4
Week 3 — Policy and User Accounts (Aug 31 – Sep 3)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Build and Join Client VM |  | Sabitha S Karanavar | Description: Create the Windows Client VM, install the client OS, join it to the domain, and verify domain login. ¦ Deliverable: Domain-joined client (screenshot).
Build OU Structure |  | Sabitha S Karanavar | Description: Create top-level department OUs and sub-OUs matching the Week 1 design. ¦ Deliverable: OU hierarchy visible in AD Users and Computers (screenshot).
Create Security Groups |  | Sabitha S Karanavar | Description: Create all security groups per the RBAC matrix, following the naming convention. ¦ Deliverable: Full group list created (screenshot).
Configure Password Policy via GPO |  | Sabitha S Karanavar | Description: Configure complexity, minimum length, lockout threshold, and expiration via Group Policy, then verify it applied. ¦ Deliverable: GPO screenshot + confirmation the policy is enforced. |  |  |  | Sabitha S Karanavar | 12800001903
Create First 15 Users |  | Sabitha S Karanavar | Description: Create the first half of the 30 employees, placed in correct OUs and groups. ¦ Deliverable: 15 accounts created and verified. |  |  |  | Sabitha S Karanavar | 12800002076
Create Remaining 15 Users |  | Sabitha S Karanavar | Description: Finish the roster and verify all 30 accounts' properties and group memberships. ¦ Deliverable: Full 30-user roster (screenshot of complete directory). |  |  |  | Sabitha S Karanavar | 12800002249
[Security Rubric] Implement Access Control Measures (ACL + Model + User Levels) |  | Sabitha S Karanavar | Description: Rubric — Network Security: Implement Access Control Measures. Create 1 standalone test shared folder now (the full departmental folder set follows in Week 4) and configure at least 1 NTFS Access Control List (ACL) on it. Document the access control model in use (DAC via NTFS permissions + RBAC via AD security groups; note how MAC would differ), and define at least 1 user access level (e.g., Standard User vs. Privileged Admin) tied to the RBAC matrix. ¦ Deliverable: ACL configuration screenshot + access-control-model write-up + user access level definition. |  |  |  | Sabitha S Karanavar
[Security Rubric] Network Security Tools + Vulnerability Assessment (combined deliverable) |  | Sabitha S Karanavar | Description: Rubric — Network Security: Utilize Network Security Tools AND Cyber Threats: Apply Vulnerability Assessment Techniques (1 combined deliverable covers both). From the Kali/Parrot VM built in Week 2: capture live traffic with Wireshark and analyze 1 capture (e.g., an AD authentication exchange from this week's new client/users). Run an OpenVAS or Nessus Essentials scan against the Server and Client VMs (document scan configuration, summary of findings, vulnerability classification). Separately run an Nmap asset-discovery scan documenting discovered systems/services, marking the Domain Controller as the critical asset, and sketch a basic network map. Run 1 penetration-testing tool (e.g., a Metasploit module or an Nmap NSE vuln script) against a deliberately unpatched test VM/service and capture the output. ¦ Deliverable: Wireshark capture + analysis; OpenVAS/Nessus vulnerability report; Nmap asset-discovery + network-map write-up; 1 pentest tool output. |  |  |  | Sabitha S Karanavar
Week 3 Status Update | [6 empty] | Sabitha S Karanavar | 12800002595
0/4
Week 4 — Entra ID Foundation (Sep 7 – Sep 10)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Build On-Prem Apps via Shared Folders |  | Sabitha S Karanavar | Description: Create shared folders for each simulated app and lock down NTFS permissions using AD security groups. ¦ Deliverable: Working folder-permission RBAC — screenshot of access difference tested across two roles.
Create Entra ID Tenant |  | Sabitha S Karanavar | Description: Stand up the Microsoft Entra ID tenant and note that real hybrid sync (Entra Connect) is out of scope for this lab. ¦ Deliverable: Active Entra tenant. |  |  |  | Sabitha S Karanavar | 12800002768
Create Cloud Users and Groups |  | Sabitha S Karanavar | Description: Create cloud users mirroring on-prem AD (bulk CSV import for PowerShell practice), plus mirrored cloud groups. ¦ Deliverable: 30 cloud users + groups, screenshot of Entra ID user list. |  |  |  | Sabitha S Karanavar | 12800002941
Build Simulated Enterprise Apps in Entra ID |  | Sabitha S Karanavar | Description: Create custom Enterprise Application objects and assign cloud groups to them. ¦ Deliverable: App-to-group assignments visible in Entra ID (screenshot). |  |  |  | Sabitha S Karanavar | 12800003114
Enable and Configure MFA |  | Sabitha S Karanavar | Description: Enable MFA in Entra ID, configure Microsoft Authenticator as the method, and enroll at least one privileged account. ¦ Deliverable: MFA policy active (screenshot). |  |  |  | Sabitha S Karanavar | 12800003287
[Security Rubric] Security Monitoring + Incident Response (combined deliverable) |  | Sabitha S Karanavar | Description: Rubric — Network Security: Monitor and Respond to Network Security Events AND Cyber Threats: Implement Security Monitoring and Incident Response (1 combined report covers both). Stand up basic monitoring (Windows Event Forwarding + a free SIEM such as Wazuh, or the Week 2 IDS alert log) with 1 detection use case (e.g., failed-logon spike) and document your alert-prioritization process (High/Med/Low triage). Simulate 1 live security incident — e.g., a brute-force/unauthorized RDP attempt against the DC launched from the Kali VM — classify it, document response steps taken, capture supporting logs/screenshots, and close with lessons learned. ¦ Deliverable: Monitoring/detection-rule setup + alert-prioritization write-up + 1 incident response report (classification, response steps, logs/screenshots, lessons learned). |  |  |  | Sabitha S Karanavar
[Security Rubric] Cyber Threat Analysis: Malware Sample, Phishing Template, APT-to-MITRE Mapping |  | Sabitha S Karanavar | Description: Rubric — Cyber Threats: Identify and Analyze Cyber Threats. Submit a publicly available malware sample hash (or an EICAR-style test file) to VirusTotal, or detonate a sample in Any.Run/Hybrid Analysis, and document detection results, behavioral indicators, and potential impact. Using the Social-Engineering Toolkit (SET) on the Kali/Parrot VM, build 1 phishing email/website template — lab use only, never sent externally — demonstrating a credential-harvesting scenario relevant to healthcare (e.g., a fake Entra ID login page, tying in nicely with this week's Entra ID build). Research 1 real-world APT campaign that has targeted healthcare and map its tactics/techniques to the MITRE ATT&CK framework. ¦ Deliverable: VirusTotal/Any.Run report; SET phishing template screenshots; APT-to-MITRE ATT&CK mapping document. |  |  |  | Sabitha S Karanavar
[Security Rubric] Threat Intelligence: IoC Analysis + OpenCTI Platform |  | Sabitha S Karanavar | Description: Rubric — Cyber Threats: Implement Threat Intelligence Principles. Analyze 2 Indicators of Compromise (IoCs) pulled from this week's malware/phishing work above, or from a public threat feed (e.g., a malicious file hash and a phishing domain), documenting the detection method used for each and how each indicates a threat. Deploy the OpenCTI Threat Intelligence Platform via Docker (or system install), configure at least 2 connectors (e.g., MITRE ATT&CK connector + AlienVault OTX or VirusTotal connector), and demonstrate basic usage by importing/viewing the 2 IoCs above. ¦ Deliverable: IoC analysis write-up (2 IoCs) + OpenCTI setup screenshots + 2-connector configuration proof + basic usage demo. |  |  |  | Sabitha S Karanavar
[Security Rubric] Risk Management: Critical Risks + Treatment + Monitoring Procedure |  | Sabitha S Karanavar | Description: Rubric — Cyber Threats: Develop and Apply Risk Management Strategies. From Week 3's vulnerability scan results, identify and document 2 critical risks with explanations, a treatment recommendation for each (mitigate/accept/transfer/avoid), and basic mitigation steps. Create 1 risk-monitoring procedure describing how these risks will be tracked going forward (recurring scan cadence, owner, review checkpoint). Finish by doing a 10-minute self-check of both rubrics against Weeks 1-4's artifacts so any gap surfaces now, not at Week 12. ¦ Deliverable: Risk register (2 critical risks + treatment + mitigation) + risk-monitoring procedure document. |  |  |  | Sabitha S Karanavar
Week 4 Status Update | [6 empty] | Sabitha S Karanavar | 12800003460
0/4
Week 5 — First JML Activities: Onboarding and Transfer (Sep 14 – Sep 17)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Verify End-to-End Access |  | Sabitha S Karanavar | Description: Test a full login flow for a regular user (domain login -> app access via group assignment) and troubleshoot any gaps. ¦ Deliverable: Confirmed working access chain for at least one role. |  |  |  | Sabitha S Karanavar | 12800003633
Activity 1 — Employee Onboarding |  | Sabitha S Karanavar | Description: Run a full onboarding scenario for a new nurse hire: create the AD account, assign groups, and provision cloud/app access. ¦ Deliverable: Onboarding executed and screenshotted. |  |  |  | Sabitha S Karanavar | 12800003806
Document Onboarding Ticket |  | Sabitha S Karanavar | Description: Write up the onboarding scenario as a completed IAM ticket using the template. ¦ Deliverable: Completed onboarding ticket + screenshots. |  |  |  | Sabitha S Karanavar | 12800003979
Activity 2 — Employee Transfer |  | Sabitha S Karanavar | Description: Simulate a department transfer (e.g., Emergency -> ICU): remove old access, grant new access. ¦ Deliverable: Transfer executed in AD/Entra (screenshot). |  |  |  | Sabitha S Karanavar | 12800004152
Week 5 Status Update | [6 empty] | Sabitha S Karanavar | 12800004325
0/4
Week 6 — Termination and MFA Support (Sep 21 – Sep 24)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Document Transfer Ticket + Retro |  | Sabitha S Karanavar | Description: Write the transfer ticket, then spend 15 minutes noting any gaps from Activities 1-2. ¦ Deliverable: Transfer ticket + short notes. |  |  |  | Sabitha S Karanavar | 12800004498
Activity 3 — Employee Termination |  | Sabitha S Karanavar | Description: Simulate a contractor termination: disable the account, strip group memberships, and remove app access. ¦ Deliverable: Terminated account fully deprovisioned (before/after screenshot). |  |  |  | Sabitha S Karanavar | 12800004671
Document Termination Ticket |  | Sabitha S Karanavar | Description: Write the termination ticket with resolution notes. ¦ Deliverable: Completed termination ticket. |  |  |  | Sabitha S Karanavar | 12800004844
Activity 4 — MFA Support |  | Sabitha S Karanavar | Description: Simulate a doctor losing their MFA device: verify identity per policy, reset MFA, and re-enroll a new device. ¦ Deliverable: MFA reset completed + screenshot. |  |  |  | Sabitha S Karanavar | 12800005017
Week 6 Status Update | [6 empty] | Sabitha S Karanavar | 12800005190
0/4
Week 7 — Access Review (Sep 28 – Oct 1)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Document MFA Ticket |  | Sabitha S Karanavar | Description: Write the MFA support ticket. ¦ Deliverable: Completed MFA ticket. |  |  |  | Sabitha S Karanavar | 12800005363
Plant Access Review Findings |  | Sabitha S Karanavar | Description: Deliberately create 2-3 realistic issues (a stale/terminated account not fully removed, an over-permissioned group membership) to make the access review realistic. ¦ Deliverable: Issues planted and noted privately (not yet "found"). |  |  |  | Sabitha S Karanavar | 12800005536
Activity 5 — Access Review |  | Sabitha S Karanavar | Description: Pull current access assignments against the RBAC baseline, identify the planted issues plus any real ones, and compile findings. ¦ Deliverable: Findings list. |  |  |  | Sabitha S Karanavar | 12800005709
Write Access Review Report + Remediate |  | Sabitha S Karanavar | Description: Write a short findings + corrective-actions report, then fix everything found the same day. ¦ Deliverable: Access review report v1 + environment restored to baseline (before/after screenshot). |  |  |  | Sabitha S Karanavar | 12800005882
Week 7 Status Update | [6 empty] | Sabitha S Karanavar | 12800006055
0/4
Week 8 — PowerShell Automation (Oct 5 – Oct 8)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
PowerShell: Query Scripts |  | Sabitha S Karanavar | Description: Write a script using Get-ADUser/Get-ADGroupMember to pull a user/group report. ¦ Deliverable: Working PowerShell script + sample output. |  |  |  | Sabitha S Karanavar | 12800006228
PowerShell: Automate Account Creation |  | Sabitha S Karanavar | Description: Script the account-creation steps from Activity 1 (create user, add to groups). ¦ Deliverable: Script that creates a new user end-to-end from one command. |  |  |  | Sabitha S Karanavar | 12800006401
PowerShell: Automate Deprovisioning |  | Sabitha S Karanavar | Description: Script the termination steps (disable account, remove group memberships) from Activity 3. ¦ Deliverable: One-command deprovisioning script. |  |  |  | Sabitha S Karanavar | 12800006574
Add Security, Reception, Contractor Roles |  | Sabitha S Karanavar | Description: Build OUs, groups, and simulated app access for the three roles not yet built. ¦ Deliverable: RBAC matrix updated and fully built out for all 10 roles. |  |  |  | Sabitha S Karanavar | 12800006747
Week 8 Status Update | [6 empty] | Sabitha S Karanavar | 12800006920
0/4
Week 9 — Expand and Repeat the Lifecycle (Oct 12 – Oct 15)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Contractor Auto-Expiration |  | Sabitha S Karanavar | Description: Set AccountExpirationDate on contractor accounts to enforce a 90-day rule. ¦ Deliverable: Contractor accounts with expiration dates set (screenshot). |  |  |  | Sabitha S Karanavar | 12800007093
Second Onboarding (Automated) |  | Sabitha S Karanavar | Description: Run a second onboarding scenario using the new PowerShell script, for one of the new roles. ¦ Deliverable: Proof the process is repeatable and automatable. |  |  |  | Sabitha S Karanavar | 12800007266
Second Transfer/Termination |  | Sabitha S Karanavar | Description: Run one more transfer and one more termination using a new role, to prove repeatability beyond the first pass. ¦ Deliverable: Executed and screenshotted. |  |  |  | Sabitha S Karanavar | 12800007439
Conditional Access Policy |  | Sabitha S Karanavar | Description: Configure a basic Conditional Access policy in Entra ID (e.g., require MFA for admin/privileged roles). ¦ Deliverable: Policy active (screenshot). |  |  |  | Sabitha S Karanavar | 12800007612
Week 9 Status Update | [6 empty] | Sabitha S Karanavar | 12800007785
0/4
Week 10 — Second Review Cycle and SOPs (Oct 19 – Oct 22)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Second Access Review |  | Sabitha S Karanavar | Description: Re-run the access review process and compare against Week 7 findings. ¦ Deliverable: Second findings list (should be shorter/cleaner). |  |  |  | Sabitha S Karanavar | 12800007958
Update User Access Matrix |  | Sabitha S Karanavar | Description: Finalize the User Access Matrix to reflect the current, fully-built state of the environment. ¦ Deliverable: Final User Access Matrix. |  |  |  | Sabitha S Karanavar | 12800008131
Draft All 4 SOPs |  | Sabitha S Karanavar | Description: Write bullet-point SOPs (not essays) for: create account, disable account, reset MFA, run access review. ¦ Deliverable: 4 short SOP documents. |  |  |  | Sabitha S Karanavar | 12800008304
Organize AD/Entra Screenshots |  | Sabitha S Karanavar | Description: Sort all screenshots into labeled folders by category. ¦ Deliverable: Clean screenshot folder structure. |  |  |  | Sabitha S Karanavar | 12800008477
Week 10 Status Update | [6 empty] | Sabitha S Karanavar | 12800008650
0/4
Week 11 — Evidence and Documentation Reconciliation (Oct 26 – Oct 29)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Organize Ticket/Report Evidence |  | Sabitha S Karanavar | Description: Sort ticket and report screenshots into a portfolio folder structure. ¦ Deliverable: Portfolio-ready evidence folder. |  |  |  | Sabitha S Karanavar | 12800008823
Reconcile the Design Document |  | Sabitha S Karanavar | Description: Update the design doc to match reality: fix the employee count everywhere, complete the RBAC table for all 10 roles, sync SDLC week labels, and remove leftover template header/footer. ¦ Deliverable: Design doc v2, fully consistent with the build. |  |  |  | Sabitha S Karanavar | 12800008996
Resume and LinkedIn Summaries |  | Sabitha S Karanavar | Description: Write 3-4 resume bullets and a LinkedIn project summary highlighting the JML lifecycle, RBAC design, and PowerShell automation. ¦ Deliverable: Resume bullets + LinkedIn post draft. |  |  |  | Sabitha S Karanavar | 12800009169
Interview Talking Points |  | Sabitha S Karanavar | Description: Prepare a walkthrough: RBAC design decisions, each JML activity, the access review findings, and what was automated. ¦ Deliverable: Talking points doc. |  |  |  | Sabitha S Karanavar | 12800009342
Week 11 Status Update | [6 empty] | Sabitha S Karanavar | 12800009515
0/4
Week 12 — Publish and Close (Nov 2 – Nov 5)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Final Proofread |  | Sabitha S Karanavar | Description: Final pass on the design doc and portfolio. ¦ Deliverable: Polished, publish-ready doc. |  |  |  | Sabitha S Karanavar | 12800009688
Publish Portfolio |  | Sabitha S Karanavar | Description: Publish the portfolio (GitHub/portfolio site) and verify all links work. ¦ Deliverable: Published portfolio. |  |  |  | Sabitha S Karanavar | 12800009861
Rubric Cross-Check |  | Sabitha S Karanavar | Description: Go through course rubric items and tag where each is already satisfied by the build. ¦ Deliverable: Rubric mapping notes. |  |  |  | Sabitha S Karanavar | 12800010034
Final Review and Closure |  | Sabitha S Karanavar | Description: Check everything against the evaluation criteria from the design doc. Confirm nothing's missing. ¦ Deliverable: Project marked complete. |  |  |  | Sabitha S Karanavar | 12800010207
Week 12 Status Update | [6 empty] | Sabitha S Karanavar | 12800010380
0/4