## KPI Framework
HVMC Risk KPI Framework — leading and lagging indicators
Version 1.0 · October 14, 2026 · owners report monthly; Security & Risk Lead consolidates
ID | Type | KPI | Definition | Unit | Better when | Thresholds (G / A / R) | Owner | Data source | Linked risks
L1 | Leading | Mitigation controls implemented | Treatments from the mitigation plan verified complete | % | Higher | G ≥ plan · A within 10 pts · R > 10 pts behind | Denise Coleman | Mitigation workbook | All
L2 | Leading | KRIs at Green | Share of the 15 automated KRIs reporting Green | % | Higher | G ≥ 90% · A 60–89% · R < 60% | Anthony Ruiz | kri_monitor.py (daily) | All
L3 | Leading | Azure checklist pass rate | 27-item CIS-aligned configuration checklist | % | Higher | G ≥ 90% · A 70–89% · R < 70% | Anthony Ruiz | Monthly checklist re-run | R01–R08, R11, R15
L4 | Leading | Phishing-resistant MFA coverage | Clinical + admin users with passkey registered | % | Higher | G ≥ 90% · A 60–89% · R < 60% | Sabitha S Karanavar | Entra auth-methods report | R12, R04
L5 | Leading | Access reviews on time | Quarterly group and contractor reviews completed by due date | % | Higher | G 100% · A ≥ 80% · R < 80% | Sabitha S Karanavar | Review log | R06, R13
L6 | Leading | HIPAA training completion | Workforce completing annual training (rolling 12 months) | % | Higher | G ≥ 95% · A 80–94% · R < 80% | Daniel Osei | HR training records | R14
G1 | Lagging | High or Critical risks | Risks rated High/Critical on the weighted model | count | Lower | G 0 · A 1–2 · R ≥ 3 | Denise Coleman | Risk register | All
G2 | Lagging | Expected annual loss (top 5) | ALE of the five quantified risks | $K | Lower | G ≤ $1M · A $1–2M · R > $2M | Brian Adeyemi | ALE model | R01, R02, R05, R12, R13
G3 | Lagging | Open HIPAA gaps | Gaps G1–G8 from the HIPAA compliance matrix | count | Lower | G 0 · A 1–3 · R ≥ 4 | Denise Coleman | HIPAA matrix | G1–G8
G4 | Lagging | Mean time to detect (hours) | Security events detected from occurrence to alert | h | Lower | G ≤ 4 h · A ≤ 24 h · R > 24 h | Anthony Ruiz | Log Analytics incidents | R01
G5 | Lagging | EHR restore time in drill (hours) | Measured recovery time in quarterly restore test vs RTO 4 h | h | Lower | G ≤ 4 h · A ≤ 8 h · R > 8 h | Fatima Ali | Restore drill record | R05
G6 | Lagging | ePHI security incidents | Confirmed incidents involving ePHI | count | Lower | G 0 · A 1 (contained) · R ≥ 1 reportable | Denise Coleman | Incident register | R02, R05, R13

## Monthly Tracking
KPI tracking — monthly actual vs target
Enter actuals in yellow cells. Status: higher-is-better G if ≥ target, A if within 10 pts; lower-is-better G if ≤ target, A if ≤ 125% of target
ID | KPI | Better when | Oct target | Oct actual | Oct status | Nov target | Nov actual | Nov status | Dec target | Dec actual | Dec status | Jan target | Jan actual | Jan status | Feb target | Feb actual | Feb status | Mar target | Mar actual | Mar status
L1 | Mitigation controls implemented | Higher | baseline | 0 |  | 44 |  |  | 88 |  |  | 100 |  |  | 100 |  |  | 100
L2 | KRIs at Green | Higher | baseline | 0 |  | 40 |  |  | 80 |  |  | 93 |  |  | 93 |  |  | 100
L3 | Azure checklist pass rate | Higher | baseline | 48 |  | 70 |  |  | 89 |  |  | 93 |  |  | 96 |  |  | 96
L4 | Phishing-resistant MFA coverage | Higher | baseline |  |  | 0 |  |  | 60 |  |  | 90 |  |  | 95 |  |  | 95
L5 | Access reviews on time | Higher | baseline | 0 |  | 100 |  |  | 100 |  |  | 100 |  |  | 100 |  |  | 100
L6 | HIPAA training completion | Higher | baseline |  |  | 40 |  |  | 70 |  |  | 95 |  |  | 95 |  |  | 95
G1 | High or Critical risks | Lower | baseline | 5 |  | 4 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0
G2 | Expected annual loss (top 5) | Lower | baseline | 2766 |  | 2000 |  |  | 1100 |  |  | 820 |  |  | 820 |  |  | 820
G3 | Open HIPAA gaps | Lower | baseline | 8 |  | 4 |  |  | 1 |  |  | 0 |  |  | 0 |  |  | 0
G4 | Mean time to detect (hours) | Lower | baseline | [5 empty] | 24 |  |  | 8 |  |  | 4 |  |  | 4
G5 | EHR restore time in drill (hours) | Lower | baseline | [5 empty] | 6 | [8 empty] | 4
G6 | ePHI security incidents | Lower | baseline |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0

## KRI Log
Automated KRI results (kri_monitor.py)
Append one block per run; Red = alert raised. First run below is live data from Azure.
Run (UTC) | KRI | Indicator | Value | Target | Status | Risk | Control | Source | Triage ticket | Closed
2026-10-14T18:34:16Z | K01 | EHR storage public network access | Enabled | Disabled | Red | R02 | C02 | az storage account show
2026-10-14T18:34:16Z | K02 | EHR storage shared-key access | True | false | Amber | R02 | C02 | az storage account show
2026-10-14T18:34:16Z | K03 | EHR blob versioning | Disabled | Enabled | Red | R05 | C05 | blob-service-properties
2026-10-14T18:34:16Z | K04 | Blob soft-delete retention (days) | 7 | ≥ 30 | Amber | R05 | C05 | blob-service-properties
2026-10-14T18:34:16Z | K05 | Data-tier explicit deny rule | Missing | Present | Red | R03 | C03 | az network nsg rule list
2026-10-14T18:34:16Z | K06 | Global Administrators | 1 | 2–4 incl. break-glass | Red | R04 | C04 | Graph directoryRoles
2026-10-14T18:34:16Z | K07 | Activity log exported to Log Analytics | 0 | ≥ 1 | Red | R01 | C01 | az monitor diagnostic-settings subscription list
2026-10-14T18:34:16Z | K08 | Activity-log alert rules | 0 | ≥ 3 | Red | R01 | C01 | az monitor activity-log alert list
2026-10-14T18:34:16Z | K09 | Network flow logs | 0 | ≥ 1 | Amber | R01 | C01 | az network watcher flow-log list
2026-10-14T18:34:16Z | K10 | Defender for Storage | Free | Standard | Amber | R11 | C06 | az security pricing show
2026-10-14T18:34:16Z | K11 | Security alert contacts | 0 | ≥ 1 | Amber | R11 | C06 | az security contact list
2026-10-14T18:34:16Z | K12 | Users can register applications | True | false | Amber | R08 | C08 | Graph authorizationPolicy
2026-10-14T18:34:16Z | K13 | Guest invitations allowed from | everyone | adminsAndGuestInviters | Amber | R08 | C08 | Graph authorizationPolicy
2026-10-14T18:34:16Z | K14 | Test/shared accounts in production | 1 | 0 | Amber | R07 | C14 | az ad user list
2026-10-14T18:34:16Z | K15 | Resource locks on production RG | 0 | ≥ 1 (accepted risk) | Amber | R15 | A01 | az lock list

## Review Process
Documented review process
Who reviews what, when, with which inputs and outputs
Cadence | Forum | Chair | Inputs | Outputs / decisions | Record
Daily | Automated KRI run | Anthony Ruiz | kri_monitor.py results | Red → ticket + notify owner within 1 business day | KRI Log
Weekly | IT status stand-up | Kevin O'Brien | Open tickets, plan tasks | Task re-plans, blockers escalated | Task board
Monthly | KPI review (Executive Risk Committee) | Denise Coleman | Monthly Tracking sheet, dashboard, checklist re-run | Amber/Red actions, budget changes, risk acceptances | Decision log
Quarterly | Board risk update | Board chair | Board pack, 6 board KPIs, control tests | Direction, appetite changes, approvals | Board minutes
Quarterly | Control effectiveness tests | Control owners | Restore drill, break-glass test, port test, access reviews | Residual re-score in register History | Risk register
Annually | Framework review | Executive Risk Committee | Year of KPI trends, incidents, regulation | Revised KPIs, thresholds, weights, appetite | Version history

## Stakeholder Plan
Stakeholder communication plan
Audience analysis, tailored message, channel, frequency and owner
Audience | Group | Members | Interest | Influence | Technical level | Information needs | Key message | Format / channel | Frequency | Owner | Feedback
Board of Directors | Governance | Board (external to tenant) | High | High | Low | Overall posture, financial exposure, decisions required, regulatory standing | HVMC's biggest cyber risks are known and fixable for under $53K this year; we ask you to approve the plan and insurance. | Quarterly board pack (slides) + dashboard summary | Quarterly; ad hoc for Critical | Denise Coleman | Board Q&A; minutes
Executive Risk Committee | Executive | CEO, CFO, CMO + Denise Coleman | High | High | Medium | Trend vs plan, budget, residual risks to accept, escalations | Plan is on track / off track; these residual risks need your acceptance. | Monthly meeting with dashboard walk-through | Monthly | Denise Coleman | Decision log
Security & Risk team | Risk owners | Denise Coleman, Anthony Ruiz | High | High | High | Live KRIs, alerts, control test results | Every Red KRI is an alert to triage within 1 business day. | Live dashboard + automated alerts (email/Teams) | Continuous; weekly stand-up | Anthony Ruiz | Alert ticket closure
IT operations | Implementers | Kevin O'Brien, Fatima Ali, Jason Park | High | Medium | High | Assigned tasks, due dates, technical detail, change windows | Phase 1 quick wins (storage, NSG, admin) by Oct 31 clear 3 of the 6 Red KRIs. | Task board + weekly status in Teams | Weekly | Kevin O'Brien | Task status updates
System & data owners | Business owners | Sarah Chen, Elena Petrova, David Patel, Grace Nguyen, Daniel Osei, Brian Adeyemi | Medium | Medium | Low | Risks to their system, downtime targets, decisions they own | Your system's recovery target is X hours; here is what changes for your team. | Monthly one-page system brief | Monthly; at go-live of changes | Denise Coleman | Owner sign-off on acceptance
Clinical workforce | End users | Doctors (5), nurses (7), lab (3), pharmacy (3) | Low | Low | Low | What changes for them (passkeys, downtime procedures), why, and when | A quick passkey sign-in protects your patients' records; here is how to set it up. | Huddle briefings, intranet notice, 2-minute how-to video | At each rollout; annual training | Sabitha S Karanavar | Help-desk ticket trends
Business staff | End users | Reception, HR, Finance | Low | Low | Low | New rules (sanction policy, training), sign-in changes | Complete your HIPAA training by Dec 13; report anything suspicious to Jason Park. | Email + team meetings | At rollout; quarterly reminder | Daniel Osei | Training completion rate
Contractor | Third party | Carlos Diaz (IT contractor) | Medium | Low | High | Access terms, BAA obligations, expiry | Your access ends on the contract date and is reviewed quarterly under the BAA. | Formal letter + BAA | At contract start/renewal | Kevin O'Brien | Signed BAA
Regulators & auditors | External | HHS OCR, external auditor | Medium | High | Medium | Evidence of risk analysis, management, and breach handling | HVMC performs and documents risk analysis and acts on it (HIPAA §164.308(a)(1)). | Formal reports on request; breach notices | On request; within 60 days of breach discovery | Privacy Officer (to be designated) | Audit findings
Cyber insurer | External | Insurance carrier / broker | Medium | Medium | Medium | Control attestations (MFA, backups, logging) | Controls C01, C05, C07 are in place and tested. | Application questionnaire; renewal attestation | Annually; at claim | Brian Adeyemi | Premium and terms

## Comms Schedule
Communication schedule
Fixed dates (Oct–Jan) and recurring cadences
When | Communication | Audience | Owner | Sent (date)
Oct 19, 2026 | Plan kick-off brief; Phase 1 tasks assigned | IT operations; Security team | Denise Coleman
Oct 21, 2026 | Board pack: risk report and plan approval request | Board; Executive Risk Committee | Denise Coleman
Oct 26, 2026 | System briefs: recovery targets and changes | System & data owners | Denise Coleman
Nov 2, 2026 | Phase 1 results: KRIs turned Green | Executive Risk Committee | Anthony Ruiz
Nov 16, 2026 | Passkey rollout notice + how-to | Clinical workforce; Business staff | Sabitha S Karanavar
Nov 30, 2026 | Monthly KPI review | Executive Risk Committee | Denise Coleman
Dec 13, 2026 | Plan completion report; residual-risk acceptance | Executive Risk Committee; owners | Denise Coleman
Jan 2027 | Quarterly board update (Q4 KPIs) | Board | Denise Coleman
Weekly | IT status stand-up | IT operations | Kevin O'Brien
Daily (automated) | kri_monitor.py run; Red KRI → alert | Security team | Anthony Ruiz
Monthly | Dashboard review + checklist re-run | Executive Risk Committee | Anthony Ruiz
Quarterly | Board pack; control tests; residual re-score | Board; owners | Denise Coleman
Annually | Strategy, weights and appetite review; insurer renewal | Board; Executive Risk Committee | Denise Coleman
Event | Critical incident: exec notice within 1 h; breach assessment; §164.404 notice ≤ 60 days | Executives; OCR; patients | Privacy Officer