## sabitha's project board
Sabitha's Project Board
Healthcare IAM Operations Home Lab — 12-Week Daily Task Breakdown
Semester 3-Week 1 — Scope Definition and First Build Steps (Aug 17 – Aug 20)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Define Organization Scenario and Scope |  |  |  | Done | 2026-08-17 | v | Sabitha S Karanavar |  | 12797429012
Build RBAC Skeleton and Simulated Application List |  |  |  | Done | 2026-08-18 | v | Sabitha S Karanavar |  | 12797433041
Research on core concepts of IAM and the Tech Stack |  |  |  | Done | 2026-08-19 | v | Sabitha S Karanavar |  | 12835099081
Research Why IAM Matters in Healthcare |  |  |  | Done | 2026-08-19 | v | Sabitha S Karanavar |  | 12856255430
[Security Rubric] Create Network Topology Diagram (LAN) |  |  |  | Done | 2026-08-20 | v | Sabitha S Karanavar |  | 12913527578
[Security Rubric] Secure Wireless Network (WPA2/WPA3 + WIPS) |  |  |  | Done | 2026-08-20 | v | Sabitha S Karanavar |  | 12913537370
Week 1 Status Update |  |  |  | Done | 2026-08-20 | v | Sabitha S Karanavar |  | 12797447391
[5 empty] | 2026-08-17 to 2026-08-20 | 7/7
Semester 3-Week 2 — Security Operations - Network Security (Aug 24 – Aug 27)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Set Up UTM and Server VM Shell and Install Ubuntu Server OS |  |  |  | Done | 2026-08-24 | v | Sabitha S Karanavar |  | 12856160005
[Security Rubric] Map OSI/TCP-IP Models, Subnet the Lab, Diagram Secure Architecture |  |  |  | Done | 2026-08-25 | v | Sabitha S Karanavar |  | 12913746940
[Security Rubric] Set Up Kali/Parrot Security Testing VM |  |  |  | Done | 2026-08-26 | v | Sabitha S Karanavar |  | 12913528988
[Security Rubric] Implement Firewall Rule, IDS, and IPS with 1 Detected Event |  |  |  | Done | 2026-08-27 | v | Sabitha S Karanavar |  | 12913529991
Week 2 Status Update |  |  |  | Done | 2026-08-27 |  | Sabitha S Karanavar |  | 12797535495
[5 empty] | 2026-08-24 to 2026-08-27 | 4/5
Semester 3-Week 3 — Security Operations - Network Security (Aug 31 – Sep 3)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
[Security Rubric] Implement Access Control Measures (ACL + Model + User Levels) |  | Sabitha S Karanavar |  | Done | 2026-08-31 | v | Sabitha S Karanavar |  | 12913541134
[Security Rubric] Network Security Tools + Vulnerability Assessment (combined deliverable) |  | Sabitha S Karanavar |  | Done | 2026-09-01 | v | Sabitha S Karanavar |  | 12913575713
[Security Rubric] Security Monitoring + Incident Response (combined deliverable) |  | Sabitha S Karanavar |  | Done | 2026-09-02 | v | Sabitha S Karanavar |  | 12913615549
[Security Rubric] Cyber Threat Analysis: Malware Sample, Phishing Template, APT-to-MITRE Mapping |  | Sabitha S Karanavar |  | Done | 2026-09-03 |  | Sabitha S Karanavar |  | 12913567959
[Security Rubric] Threat Intelligence: IoC Analysis + OpenCTI Platform |  | Sabitha S Karanavar |  | Done | 2026-09-03 |  | Sabitha S Karanavar |  | 12913578890
[Security Rubric] Risk Management: Critical Risks + Treatment + Monitoring Procedure |  | Sabitha S Karanavar |  | Done | 2026-09-03 |  | Sabitha S Karanavar |  | 12913576457
Promote to Domain Controller |  | Sabitha S Karanavar |  | Working on it | 2026-09-03 |  | Sabitha S Karanavar |  | 12797437788
Build and Join Client VM |  | Sabitha S Karanavar |  | Working on it | 2026-09-03 |  | Sabitha S Karanavar |  | 12797455650
[5 empty] | 2026-08-31 to 2026-09-03 | 3/8
Semester 3-Week 4 — Security Operations - Network Security (Sep 7– Sep 10)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Build On-Prem Apps via Shared Folders |  |  |  |  | 2026-09-07 |  | Sabitha S Karanavar |  | 12797594910
Create Entra ID Tenant |  |  |  |  | 2026-09-07 |  | Sabitha S Karanavar |  | 12797623999
Create Cloud Users and Groups |  |  |  |  | 2026-09-08 |  | Sabitha S Karanavar |  | 12797645260
Build Simulated Enterprise Apps in Entra ID |  |  |  |  | 2026-09-09 |  | Sabitha S Karanavar |  | 12797645436
Enable and Configure MFA |  |  |  |  | 2026-09-09 |  | Sabitha S Karanavar |  | 12797609720
Build OU Structure |  |  |  |  | 2026-09-10 |  | Sabitha S Karanavar |  | 12797420432
Create Security Groups |  |  |  |  | 2026-09-10 |  | Sabitha S Karanavar |  | 12797535239
Configure Password Policy via GPO |  |  |  |  | 2026-09-10 |  | Sabitha S Karanavar |  | 12797539166
Create First 15 Users |  |  |  |  | 2026-09-10 |  | Sabitha S Karanavar |  | 12797522257
Create Remaining 15 Users |  |  |  |  | 2026-09-10 |  | Sabitha S Karanavar |  | 12797547053
Week 4 Status Update |  |  |  |  | 2026-09-10 | v | Sabitha S Karanavar |  | 12797600712
[5 empty] | 2026-09-07 to 2026-09-10 | 1/11
Semester 4 -Week 5 — First JML Activities: Onboarding & Transfer + Cloud Security Foundations (Sep 14 – Sep 19)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Verify End-to-End Access |  |  |  |  | 2026-09-14 |  | Sabitha S Karanavar |  | 12797670532
[Cloud Security Rubric] Cloud Fundamentals & Shared Responsibility: Data Classification, S3 Encryption, IaaS/PaaS/SaaS Map |  |  |  |  | 2026-09-15 |  | Sabitha S Karanavar
[Cloud Security Rubric] NIST Cloud Risk Assessment: 5 Risks + Mitigations + Risk Assessment Report |  |  |  |  | 2026-09-16 |  | Sabitha S Karanavar
[Cloud Security Rubric] Cloud Architecture: Three-Tier Diagram + VPC Build (Subnets, Security Groups, NACLs) |  |  |  |  | 2026-09-17 |  | Sabitha S Karanavar
[Cloud Security Rubric] Security Design Patterns: Bastion Host + Zero Trust Implementation (2 Patterns) |  |  |  |  | 2026-09-18 |  | Sabitha S Karanavar
Activity 1 — Employee Onboarding + [Cloud/IAM Rubric] AWS IAM User/Group/Role Provisioning with MFA (Least Privilege) |  |  |  |  | 2026-09-18 |  | Sabitha S Karanavar
Document Onboarding Ticket |  |  |  |  | 2026-09-19 |  | Sabitha S Karanavar
Activity 2 — Employee Transfer |  |  |  |  | 2026-09-19 |  | Sabitha S Karanavar
Week 5 Status Update | [6 empty] | Sabitha S Karanavar |  | 12797641537
[5 empty] | 2026-09-14 to 2026-09-19 | 0/9
Semester 4-Week 6 — Termination, MFA Support & Cloud Infrastructure/Identity (Sep 21 – Sep 26)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Document Transfer Ticket + Retro |  |  |  |  | 2026-09-21 |  | Sabitha S Karanavar |  | 12821658303
[Cloud Security Rubric] Cloud Infrastructure Security: Harden Cloud VM (Automated Patching, Host Firewall, Secure SSH) |  |  |  |  | 2026-09-22 |  | Sabitha S Karanavar
[Cloud Security Rubric] Container & Serverless Security: Secure Dockerfile + Trivy Scan + Hardened Serverless Function |  |  |  |  | 2026-09-23 |  | Sabitha S Karanavar
Activity 3 — Employee Termination + [Cloud/IAM Rubric] AWS IAM Deprovisioning + Custom JSON Policy & ABAC Resource-Tag Review |  |  |  |  | 2026-09-24 |  | Sabitha S Karanavar
Document Termination Ticket |  |  |  |  | 2026-09-25 |  | Sabitha S Karanavar
[Compliance Rubric] Compliance Fundamentals: HIPAA + 1 Additional Framework, Requirements Analysis, Program Plan, 2 Controls |  |  |  |  | 2026-09-25 |  | Sabitha S Karanavar
Activity 4 — MFA Support + [Cloud/IAM Rubric] SAML Federation Setup + Authentication Testing Evidence |  |  |  |  | 2026-09-26 |  | Sabitha S Karanavar
[Compliance Rubric] Compliance Program Development: Governance Model, Policy Document, Training Plan |  |  |  |  | 2026-09-26 |  | Sabitha S Karanavar
Week 6 Status Update | [6 empty] | Sabitha S Karanavar |  | 12821626719
[5 empty] | 2026-09-21 to 2026-09-26 | 0/9
Semester 4- Week 7 — Access Review, Cloud Compliance & Incident Response (Sep 28 – Oct 3)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Document MFA Ticket |  |  |  |  | 2026-09-28 |  | Sabitha S Karanavar |  | 12821668424
[Cloud Security Rubric] Cloud Security Operations: Centralized Logging + Monitoring (CloudTrail, VPC Flow Logs, GuardDuty, Dashboard) |  |  |  |  | 2026-09-29 |  | Sabitha S Karanavar
Plant Access Review Findings + [Compliance Rubric] Audit Plan + Evidence Collection (3 Controls) |  |  |  |  | 2026-09-30 |  | Sabitha S Karanavar
Activity 5 — Access Review + [Cloud/Compliance Rubric] Multi-System Compliance Assessment (Map to CIS/NIST/HIPAA + Gap Analysis) |  |  |  |  | 2026-10-01 |  | Sabitha S Karanavar
Write Access Review Report + Remediate + [Cloud/Compliance Rubric] Governance Automation (AWS Orgs/SCPs/Tagging/Config Rules) + Compliance Status Report, Record Mgmt & KPI Monitoring |  |  |  |  | 2026-10-02 |  | Sabitha S Karanavar
[Cloud Security Rubric] Cloud Incident Response Playbook (Identification, Containment, Investigation, Eradication, Recovery) — Developed + Tested |  |  |  |  | 2026-10-03 |  | Sabitha S Karanavar
[Compliance Rubric] Legal & Ethical Implementation: Obligations Matrix + Ethical Framework + Compliance Risk Assessment + Incident Scenario |  |  |  |  | 2026-10-03 |  | Sabitha S Karanavar
Week 7 Status Update | [6 empty] | Sabitha S Karanavar |  | 12821698898
[5 empty] | 2026-09-28 to 2026-10-03 | 0/8
Semester 4- Week 8 — PowerShell Automation (Oct 5 – Oct 8)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
PowerShell: Query Scripts |  |  |  |  | 2026-10-05 |  | Sabitha S Karanavar |  | 12821698865
PowerShell: Automate Account Creation |  |  |  |  | 2026-10-06 |  | Sabitha S Karanavar |  | 12821734182
PowerShell: Automate Deprovisioning |  |  |  |  | 2026-10-07 |  | Sabitha S Karanavar |  | 12821669116
Add Security, Reception, Contractor Roles |  |  |  |  | 2026-10-08 |  | Sabitha S Karanavar |  | 12821704818
Week 8 Status Update | [6 empty] | Sabitha S Karanavar |  | 12821691612
[5 empty] | 2026-10-05 to 2026-10-08 | 0/5
Week 9 — Expand and Repeat the Lifecycle (Oct 12 – Oct 15)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Contractor Auto-Expiration |  |  |  |  | 2026-10-12 |  | Sabitha S Karanavar |  | 12821744716
Second Onboarding (Automated) |  |  |  |  | 2026-10-13 |  | Sabitha S Karanavar |  | 12821745211
Second Transfer/Termination |  |  |  |  | 2026-10-14 |  | Sabitha S Karanavar |  | 12821760799
Conditional Access Policy |  |  |  |  | 2026-10-15 |  | Sabitha S Karanavar |  | 12821756380
Week 9 Status Update | [6 empty] | Sabitha S Karanavar |  | 12821753181
[5 empty] | 2026-10-12 to 2026-10-15 | 0/5
Week 10 — Second Review Cycle and SOPs (Oct 19 – Oct 22)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Second Access Review |  |  |  |  | 2026-10-19 |  | Sabitha S Karanavar |  | 12821739463
Update User Access Matrix |  |  |  |  | 2026-10-20 |  | Sabitha S Karanavar |  | 12821729837
Draft All 4 SOPs |  |  |  |  | 2026-10-21 |  | Sabitha S Karanavar |  | 12821769361
Organize AD/Entra Screenshots |  |  |  |  | 2026-10-22 |  | Sabitha S Karanavar |  | 12821792905
Week 10 Status Update | [6 empty] | Sabitha S Karanavar |  | 12821790938
[5 empty] | 2026-10-19 to 2026-10-22 | 0/5
Week 11 — Evidence and Documentation Reconciliation (Oct 26 – Oct 29)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Organize Ticket/Report Evidence |  |  |  |  | 2026-10-26 |  | Sabitha S Karanavar |  | 12821791541
Reconcile the Design Document |  |  |  |  | 2026-10-27 |  | Sabitha S Karanavar |  | 12821794030
Resume and LinkedIn Summaries |  |  |  |  | 2026-10-28 |  | Sabitha S Karanavar |  | 12821761498
Interview Talking Points |  |  |  |  | 2026-10-29 |  | Sabitha S Karanavar |  | 12821783211
Week 11 Status Update | [6 empty] | Sabitha S Karanavar |  | 12821761644
[5 empty] | 2026-10-26 to 2026-10-29 | 0/5
Week 12 — Publish and Close (Nov 2 – Nov 5)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Text 1 | Item ID (auto generated)
Final Proofread |  |  |  |  | 2026-11-02 |  | Sabitha S Karanavar |  | 12821816190
Publish Portfolio |  |  |  |  | 2026-11-03 |  | Sabitha S Karanavar |  | 12821789142
Rubric Cross-Check |  |  |  |  | 2026-11-04 |  | Sabitha S Karanavar |  | 12821813670
Final Review and Closure |  |  |  |  | 2026-11-05 |  | Sabitha S Karanavar |  | 12821832278
[5 empty] | 2026-11-02 to 2026-11-05 | 0/4

## updates
Sabitha's Project Board | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
12797429012 | Define Organization Scenario and Scope | Update |  | Sabitha S Karanavar | 13/August/2026 06:46:32 PM | Description: Define the fictional hospital's name, confirm 30 employees, list departments and roles, write a one-paragraph project scope statement, and note what's out of scope (no custom app, no real hybrid sync). ¦ Deliverable: One-page scenario write-up + department list. | 0 |  | 5459063534
12797433041 | Build RBAC Skeleton and Simulated Application List | Update |  | Sabitha S Karanavar | 13/August/2026 06:47:07 PM | Description: For each department, define its simulated application (shared folder + future Entra app pairing), sketch the OU structure, and decide the security group naming convention. ¦ Deliverable: RBAC matrix v1 (role -> app -> access level) + OU sketch. | 0 |  | 5459065863
12797437788 | Promote to Domain Controller | Update |  | Sabitha S Karanavar | 13/August/2026 06:48:11 PM | Description: Install samba, krb5-user, and winbind on the Ubuntu Server VM; provision the domain with samba-tool domain provision --use-rfc2307; point the server's DNS resolver at Samba's internal DNS and disable systemd-resolved's port-53 stub listener so it doesn't conflict; replace smb.conf/krb5.conf with the ones Samba generates; start the samba-ad-dc service. ¦ Deliverable: Functioning Samba4 AD Domain Controller (screenshot of samba-tool domain info output and a successful SRV lookup, e.g. host -t SRV _ldap._tcp.<yourdomain>). | 0 |  | 5459070616
12797455650 | Build and Join Client VM | Update |  | Sabitha S Karanavar | 13/August/2026 06:48:34 PM | Description: Create the client VM (Windows 10/11, or a Linux client using realmd/sssd if you'd rather stay Linux-only), install the OS, join it to the Samba domain the same way you would a Windows DC, and verify a domain login. ¦ Deliverable: Domain-joined client, confirmed with a successful domain login (screenshot). | 0 |  | 5459072305
12797420432 | Build OU Structure | Update |  | Sabitha S Karanavar | 13/August/2026 06:48:53 PM | Description: Create top-level department OUs and sub-OUs matching the Week 1 design, either with samba-tool ou create run on the server, or via Active Directory Users and Computers through RSAT installed on the joined Windows client (RSAT works fine against Samba since it only needs LDAP). ¦ Deliverable: OU hierarchy visible in ADUC or in samba-tool ou list output (screenshot). | 0 |  | 5459073743
12797535239 | Create Security Groups | Update |  | Sabitha S Karanavar | 13/August/2026 06:49:39 PM | Description: Create all security groups per the RBAC matrix, following your naming convention, using samba-tool group add on the server or ADUC via RSAT. ¦ Deliverable: Full group list created (screenshot). | 0 |  | 5459077354
12797535495 | Week 2 Status Update | Update |  | Sabitha S Karanavar | 25/August/2026 08:00:35 PM | Description: Summarize the week: note the Windows Server AD DS → Samba4 AD DC substitution and why (UTM/Ubuntu Server replaced the Windows Server VM), confirm domain provisioning, client join, OU structure, and security groups are all complete, and flag ahead that Week 3's GPO step and Week 8's PowerShell automation will need Samba-specific workarounds. ¦ Deliverable: Status update entry + a progress screenshot of the domain, OUs, and groups. | 0 |  | 5491123214
12797539166 | Configure Password Policy via GPO | Update |  | Sabitha S Karanavar | 13/August/2026 06:50:53 PM | Description: Configure complexity, minimum length, lockout threshold, and expiration via Group Policy, then verify it applied. ¦ Deliverable: GPO screenshot + confirmation the policy is enforced. | 0 |  | 5459083678
12797522257 | Create First 15 Users | Update |  | Sabitha S Karanavar | 13/August/2026 06:52:16 PM | Description: Create the first half of the 30 employees, placed in correct OUs and groups. ¦ Deliverable: 15 accounts created and verified. | 0 |  | 5459090467
12797547053 | Create Remaining 15 Users | Update |  | Sabitha S Karanavar | 13/August/2026 06:52:49 PM | Description: Finish the roster and verify all 30 accounts' properties and group memberships. ¦ Deliverable: Full 30-user roster (screenshot of complete directory). | 0 |  | 5459093049
12797594910 | Build On-Prem Apps via Shared Folders | Update |  | Sabitha S Karanavar | 13/August/2026 07:00:07 PM | Description: Create shared folders for each simulated app and lock down NTFS permissions using AD security groups. ¦ Deliverable: Working folder-permission RBAC — screenshot of access difference tested across two roles. | 0 |  | 5459121063
12797623999 | Create Entra ID Tenant | Update |  | Sabitha S Karanavar | 13/August/2026 07:01:41 PM | Description: Stand up the Microsoft Entra ID tenant and note that real hybrid sync (Entra Connect) is out of scope for this lab. ¦ Deliverable: Active Entra tenant. | 0 |  | 5459126909
12797645260 | Create Cloud Users and Groups | Update |  | Sabitha S Karanavar | 13/August/2026 07:02:05 PM | Description: Create cloud users mirroring on-prem AD (bulk CSV import for PowerShell practice), plus mirrored cloud groups. ¦ Deliverable: 30 cloud users + groups, screenshot of Entra ID user list. | 0 |  | 5459128427
12797645436 | Build Simulated Enterprise Apps in Entra ID | Update |  | Sabitha S Karanavar | 13/August/2026 07:02:36 PM | Description: Create custom Enterprise Application objects and assign cloud groups to them. ¦ Deliverable: App-to-group assignments visible in Entra ID (screenshot). | 0 |  | 5459130189
12797609720 | Enable and Configure MFA | Update |  | Sabitha S Karanavar | 13/August/2026 07:02:49 PM | Description: Enable MFA in Entra ID, configure Microsoft Authenticator as the method, and enroll at least one privileged account. ¦ Deliverable: MFA policy active (screenshot). | 0 |  | 5459130913
12797670532 | Verify End-to-End Access | Update |  | Sabitha S Karanavar | 13/August/2026 07:05:15 PM | Description: Test a full login flow for a regular user (domain login -> app access via group assignment) and troubleshoot any gaps. ¦ Deliverable: Confirmed working access chain for at least one role. | 0 |  | 5459147631
12797670532 | Verify End-to-End Access | Update |  | Abhinav Piratla | 14/September/2026 04:03:02 PM |  | 0 | 3246266604, 3246266605 | 5545574768
12797670532 | Verify End-to-End Access |  | Reply | Abhinav Piratla | 14/September/2026 04:03:16 PM | @Sabitha S Karanavar Let me know if you cannot access | 0 |  | 5545576341 | 5545574768
12797670532 | Verify End-to-End Access |  | Reply | Sabitha S Karanavar | 14/September/2026 04:10:56 PM | Thank you @Abhinav Piratla . I can see the rubrics, cloud security and compliance 1 final project submission. | 0 |  | 5545616804 | 5545574768
12797679807 | Activity 1 — Employee Onboarding | Update |  | Sabitha S Karanavar | 13/August/2026 07:05:26 PM | Description: Run a full onboarding scenario for a new nurse hire: create the AD account, assign groups, and provision cloud/app access. ¦ Deliverable: Onboarding executed and screenshotted. | 0 |  | 5459148342
12797681853 | Document Onboarding Ticket | Update |  | Sabitha S Karanavar | 13/August/2026 07:05:38 PM | Description: Write up the onboarding scenario as a completed IAM ticket using the template. ¦ Deliverable: Completed onboarding ticket + screenshots. | 0 |  | 5459149033
12797641359 | Activity 2 — Employee Transfer | Update |  | Sabitha S Karanavar | 13/August/2026 07:06:07 PM | Description: Simulate a department transfer (e.g., Emergency -> ICU): remove old access, grant new access. ¦ Deliverable: Transfer executed in AD/Entra (screenshot). | 0 |  | 5459150841
12821658303 | Document Transfer Ticket + Retro | Update |  | Sabitha S Karanavar | 17/August/2026 03:29:33 PM | Description: Write the transfer ticket, then spend 15 minutes noting any gaps from Activities 1-2. ¦ Deliverable: Transfer ticket + short notes. | 0 |  | 5466478195
12821628018 | Activity 3 — Employee Termination | Update |  | Sabitha S Karanavar | 17/August/2026 03:30:06 PM | Description: Simulate a contractor termination: disable the account, strip group memberships, and remove app access. ¦ Deliverable: Terminated account fully deprovisioned (before/after screenshot). | 0 |  | 5466482967
12821658553 | Document Termination Ticket | Update |  | Sabitha S Karanavar | 17/August/2026 03:30:43 PM | Description: Write the termination ticket with resolution notes. ¦ Deliverable: Completed termination ticket. | 0 |  | 5466488017
12821725520 | Activity 4 — MFA Support | Update |  | Sabitha S Karanavar | 17/August/2026 03:32:06 PM | Description: Simulate a doctor losing their MFA device: verify identity per policy, reset MFA, and re-enroll a new device. ¦ Deliverable: MFA reset completed + screenshot. | 0 |  | 5466494155
12821668424 | Document MFA Ticket | Update |  | Sabitha S Karanavar | 17/August/2026 03:32:54 PM | Description: Write the MFA support ticket. ¦ Deliverable: Completed MFA ticket. | 0 |  | 5466502869
12821726130 | Plant Access Review Findings | Update |  | Sabitha S Karanavar | 17/August/2026 03:33:12 PM | Description: Deliberately create 2-3 realistic issues (a stale/terminated account not fully removed, an over-permissioned group membership) to make the access review realistic. ¦ Deliverable: Issues planted and noted privately (not yet "found"). | 0 |  | 5466504107
12821628745 | Activity 5 — Access Review | Update |  | Sabitha S Karanavar | 17/August/2026 03:33:33 PM | Description: Pull current access assignments against the RBAC baseline, identify the planted issues plus any real ones, and compile findings. ¦ Deliverable: Findings list. | 0 |  | 5466505433
12821665310 | Write Access Review Report + Remediate | Update |  | Sabitha S Karanavar | 17/August/2026 03:34:02 PM | Description: Write a short findings + corrective-actions report, then fix everything found the same day. ¦ Deliverable: Access review report v1 + environment restored to baseline (before/after screenshot). | 0 |  | 5466507450
12821698865 | PowerShell: Query Scripts | Update |  | Sabitha S Karanavar | 17/August/2026 03:34:54 PM | Description: Write a script using Get-ADUser/Get-ADGroupMember to pull a user/group report. ¦ Deliverable: Working PowerShell script + sample output. | 0 |  | 5466510825
12821734182 | PowerShell: Automate Account Creation | Update |  | Sabitha S Karanavar | 17/August/2026 03:35:13 PM | Description: Script the account-creation steps from Activity 1 (create user, add to groups). ¦ Deliverable: Script that creates a new user end-to-end from one command. | 0 |  | 5466512228
12821669116 | PowerShell: Automate Deprovisioning | Update |  | Sabitha S Karanavar | 17/August/2026 03:35:26 PM | Description: Script the termination steps (disable account, remove group memberships) from Activity 3. ¦ Deliverable: One-command deprovisioning script. | 0 |  | 5466513030
12821704818 | Add Security, Reception, Contractor Roles | Update |  | Sabitha S Karanavar | 17/August/2026 03:35:45 PM | Description: Build OUs, groups, and simulated app access for the three roles not yet built. ¦ Deliverable: RBAC matrix updated and fully built out for all 10 roles. | 0 |  | 5466514352
12821744716 | Contractor Auto-Expiration | Update |  | Sabitha S Karanavar | 17/August/2026 03:36:31 PM | Description: Set AccountExpirationDate on contractor accounts to enforce a 90-day rule. ¦ Deliverable: Contractor accounts with expiration dates set (screenshot). | 0 |  | 5466521205
12821745211 | Second Onboarding (Automated) | Update |  | Sabitha S Karanavar | 17/August/2026 03:36:43 PM | Description: Run a second onboarding scenario using the new PowerShell script, for one of the new roles. ¦ Deliverable: Proof the process is repeatable and automatable. | 0 |  | 5466521971
12821760799 | Second Transfer/Termination | Update |  | Sabitha S Karanavar | 17/August/2026 03:37:02 PM | Description: Run one more transfer and one more termination using a new role, to prove repeatability beyond the first pass. ¦ Deliverable: Executed and screenshotted. | 0 |  | 5466523269
12821756380 | Conditional Access Policy | Update |  | Sabitha S Karanavar | 17/August/2026 03:37:23 PM | Description: Configure a basic Conditional Access policy in Entra ID (e.g., require MFA for admin/privileged roles). ¦ Deliverable: Policy active (screenshot). | 0 |  | 5466524577
12821739463 | Second Access Review | Update |  | Sabitha S Karanavar | 17/August/2026 03:38:39 PM | Description: Re-run the access review process and compare against Week 7 findings. ¦ Deliverable: Second findings list (should be shorter/cleaner). | 0 |  | 5466529244
12821729837 | Update User Access Matrix | Update |  | Sabitha S Karanavar | 17/August/2026 03:38:53 PM | Description: Finalize the User Access Matrix to reflect the current, fully-built state of the environment. ¦ Deliverable: Final User Access Matrix. | 0 |  | 5466530169
12821769361 | Draft All 4 SOPs | Update |  | Sabitha S Karanavar | 17/August/2026 03:39:05 PM | Description: Write bullet-point SOPs (not essays) for: create account, disable account, reset MFA, run access review. ¦ Deliverable: 4 short SOP documents. | 0 |  | 5466530953
12821792905 | Organize AD/Entra Screenshots | Update |  | Sabitha S Karanavar | 17/August/2026 03:39:24 PM | Description: Sort all screenshots into labeled folders by category. ¦ Deliverable: Clean screenshot folder structure. | 0 |  | 5466532285
12821791541 | Organize Ticket/Report Evidence | Update |  | Sabitha S Karanavar | 17/August/2026 03:41:00 PM | Description: Sort ticket and report screenshots into a portfolio folder structure. ¦ Deliverable: Portfolio-ready evidence folder. | 0 |  | 5466538580
12821794030 | Reconcile the Design Document | Update |  | Sabitha S Karanavar | 17/August/2026 03:41:12 PM | Description: Update the design doc to match reality: fix the employee count everywhere, complete the RBAC table for all 10 roles, sync SDLC week labels, and remove leftover template header/footer. ¦ Deliverable: Design doc v2, fully consistent with the build. | 0 |  | 5466539366
12821761498 | Resume and LinkedIn Summaries | Update |  | Sabitha S Karanavar | 17/August/2026 03:41:48 PM | Description: Write 3-4 resume bullets and a LinkedIn project summary highlighting the JML lifecycle, RBAC design, and PowerShell automation. ¦ Deliverable: Resume bullets + LinkedIn post draft. | 0 |  | 5466541730
12821783211 | Interview Talking Points | Update |  | Sabitha S Karanavar | 17/August/2026 03:42:01 PM | Description: Prepare a walkthrough: RBAC design decisions, each JML activity, the access review findings, and what was automated. ¦ Deliverable: Talking points doc. | 0 |  | 5466542687
12821816190 | Final Proofread | Update |  | Sabitha S Karanavar | 17/August/2026 03:43:40 PM | Description: Final pass on the design doc and portfolio. ¦ Deliverable: Polished, publish-ready doc. | 0 |  | 5466549477
12821789142 | Publish Portfolio | Update |  | Sabitha S Karanavar | 17/August/2026 03:43:28 PM | Description: Publish the portfolio (GitHub/portfolio site) and verify all links work. ¦ Deliverable: Published portfolio. | 0 |  | 5466548664
12821813670 | Rubric Cross-Check | Update |  | Sabitha S Karanavar | 17/August/2026 03:43:16 PM | Description: Go through course rubric items and tag where each is already satisfied by the build. ¦ Deliverable: Rubric mapping notes. | 0 |  | 5466547869
12821832278 | Final Review and Closure | Update |  | Sabitha S Karanavar | 17/August/2026 03:43:03 PM | Description: Check everything against the evaluation criteria from the design doc. Confirm nothing's missing. ¦ Deliverable: Project marked complete. | 0 |  | 5466547135
12835099081 | Research on core concepts of IAM and the Tech Stack | Update |  | Sabitha S Karanavar | 18/August/2026 05:43:01 PM | https://sabi-s.github.io/dae-6-month-Sabi/ | 0 |  | 5470732047
12835099081 | Research on core concepts of IAM and the Tech Stack | Update |  | Sabitha S Karanavar | 20/August/2026 05:09:22 PM | Research | 0 |  | 5478167063
12856255430 | Research Why IAM Matters in Healthcare | Update |  | Sabitha S Karanavar | 20/August/2026 05:09:36 PM | Research | 0 |  | 5478167819
12856160005 | Set Up UTM and Server VM Shell and Install Ubuntu Server OS | Update |  | Sabitha S Karanavar | 27/August/2026 03:44:10 PM | I configured UTM setup and Linux Ubuntu Server as am using Mac. | 0 |  | 5497242733
12913527578 | [Security Rubric] Create Network Topology Diagram (LAN) | Update |  | Sabitha S Karanavar | 27/August/2026 04:38:13 PM | Description: Rubric — Network Security: Understand and Implement Network Topologies. Diagram the home-lab LAN topology (host machine, Server VM, Client VM, virtual switch/NAT network) using diagrams.net or similar, showing IP addressing. Write a short explanation of how this LAN topology supports secure communication and centralized network management via the domain controller. ¦ Deliverable: Network topology diagram (1 config: LAN) + 1/2-page explanation. | 0 |  | 5497457722
12913537370 | [Security Rubric] Secure Wireless Network (WPA2/WPA3 + WIPS) | Update |  | Sabitha S Karanavar | 27/August/2026 04:38:47 PM | Description: Rubric — Network Security: Secure Wireless Networks. Configure WPA2 or WPA3 security on your home Wi-Fi router (or a simulated AP in Packet Tracer/GNS3 if a physical router isn't available) for 1 network, and document a Wireless Intrusion Prevention System (WIPS) approach — enable a router's built-in rogue-AP/WIPS feature, or set up Kismet to detect unauthorized wireless access. This one is independent of the VM build, so it's a good task to knock out early. ¦ Deliverable: WPA2/WPA3 configuration screenshot + WIPS documentation. | 0 |  | 5497459578
12913528988 | [Security Rubric] Set Up Kali/Parrot Security Testing VM | Update |  | Sabitha S Karanavar | 27/August/2026 04:56:15 PM | Description: Rubric — Network Security: Design Network Protocols and Architectures. Create a network diagram mapping the OSI 7-layer model and TCP/IP 4-layer model to the Server VM's traffic (e.g., AD DS communication) for 1 device, calculate and document proper subnetting for the lab's subnet (network/broadcast address, usable host range, mask), and extend the diagram into a secure network architecture that labels where security protocols apply (Kerberos for AD auth, LDAPS, SMB signing, TLS). ¦ Deliverable: OSI/TCP-IP + subnetting diagram + secure-architecture protocol map. | 0 |  | 5497523960
12913529991 | [Security Rubric] Implement Firewall Rule, IDS, and IPS with 1 Detected Event | Update |  | Sabitha S Karanavar | 27/August/2026 04:58:29 PM | Description: Rubric — Network Security: Implement Network Security Fundamentals. Configure 1 Windows Firewall (or pfSense, if you add a virtual firewall VM) rule restricting a specific port/app on the Server VM, install and configure Suricata or Snort as an IDS in detection mode, and configure IPS/blocking mode for 1 rule. Generate 1 example detected event by running an Nmap scan or a burst of failed RDP logins from the Kali VM you just built, and capture the alert. ¦ Deliverable: Firewall rule screenshot + IDS config + IPS config + 1 detected-event log/alert screenshot. | 0 |  | 5497538173
12913541134 | [Security Rubric] Implement Access Control Measures (ACL + Model + User Levels) | Update |  | Sabitha S Karanavar | 27/August/2026 05:17:06 PM | [Security Rubric] Implement Access Control Measures (ACL + Model + User Levels) | 0 |  | 5497603764
12913575713 | [Security Rubric] Network Security Tools + Vulnerability Assessment (combined deliverable) | Update |  | Sabitha S Karanavar | 27/August/2026 05:17:23 PM | [Security Rubric] Network Security Tools + Vulnerability Assessment (combined deliverable) | 0 |  | 5497604852
12913746940 | [Security Rubric] Map OSI/TCP-IP Models, Subnet the Lab, Diagram Secure Architecture | Update |  | Sabitha S Karanavar | 27/August/2026 04:58:05 PM | Description: Prep for the Network Security Tools, Vulnerability Assessment, and Cyber Threat Analysis rubric items coming later this week and in Weeks 3-4. Install Kali Linux or Parrot OS in VirtualBox on the same lab network segment as the Server VM and verify connectivity (ping / Nmap ping sweep). Install/update Wireshark, Nmap, a vulnerability scanner (OpenVAS or Nessus Essentials), Metasploit Framework, and the Social-Engineering Toolkit (SET). ¦ Deliverable: Running Kali/Parrot VM with tool versions confirmed + successful ping/scan reaching the Server VM (screenshot). | 0 |  | 5497536720