## Controls
HVMC Risk Mitigation Plan — Selected Controls
October 14, 2026 · Labour $75/h (cell B3) · one-time cost amortized over 3 years (cell D3) · yellow = inputs
Labour $/h | 75 | Amortize (years) | 3
ID | Control | Strategy | Treats | Description | NIST CSF 2.0 | ISO/IEC 27001:2022 Annex A | Owner | Labour hours | Other one-time $ | One-time cost | Annual cost | Annualized cost | Phase | Start week | Weeks | Objectives | Rationale
C01 | Central logging, alerting and flow logs | Mitigate | R01 | Log Analytics workspace; subscription activity log, storage and Entra audit logs via diagnostic settings; activity-log alert rules for NSG/policy/role changes; VNet flow logs | DE.CM-01, DE.CM-09, DE.AE-02 | 8.15 Logging; 8.16 Monitoring activities | Fatima Ali | 24 | 0 |  | 331 |  | 2 | 3 | 2 | O2, O3, O1 | Closes the top-ranked risk; detection is a prerequisite for every other response. Required by HIPAA §164.312(b).
C02 | EHR storage network lockdown | Mitigate | R02 | Disable public network access and shared-key auth on hvmcehrstorage; private endpoint in HVMC-Data-Subnet; access only via Entra RBAC | PR.AA-05, PR.DS-01, PR.IR-01 | 8.3 Information access restriction; 8.20 Networks security; 5.23 Cloud services | Fatima Ali | 16 | 0 |  | 90 |  | 1 | 1 | 1 | O2, O3 | One leaked key currently exposes all ePHI; private access removes the internet path entirely.
C03 | Enforced network segmentation | Mitigate | R03 | Explicit Deny-All-VNet-Inbound (priority 4000) on Data and App NSGs; Azure Policy to audit NSGs lacking the rule | PR.IR-01, PR.PS-01 | 8.22 Segregation of networks; 8.20 Networks security | Fatima Ali | 8 | 0 |  | 0 |  | 1 | 1 | 1 | O1, O2 | Default AllowVnetInBound undoes the three-tier design; a deny rule restores it at zero licence cost.
C04 | Privileged access resilience | Mitigate | R04 | Two cloud-only break-glass Global Admins (offline credentials, sign-in alert); second named admin; Privileged Identity Management for just-in-time elevation | PR.AA-05, GV.RR-02 | 8.2 Privileged access rights; 5.3 Segregation of duties | Sabitha S Karanavar | 8 | 0 |  | 216 |  | 1 | 1 | 1 | O1, O2 | Removes the single point of failure found in the BIA; PIM needs Entra ID P2 for 2 admins (2 × $9/month).
C05 | Ransomware-resilient recovery | Mitigate | R05 | Blob versioning; 30-day soft delete; Azure Backup vaulted backup with immutability; quarterly restore test against BIA RTO 4 h / RPO 15 min | PR.DS-11, PR.IR-03, RC.RP-01 | 8.13 Information backup; 8.14 Redundancy; 5.30 ICT readiness for business continuity | Fatima Ali | 16 | 0 |  | 2400 |  | 2 | 3 | 3 | O1, O4, O2 | Versioning is off today, so encrypted blobs cannot be rolled back; this meets the BIA RPO.
C06 | Malware scanning for EHR uploads | Mitigate | R11 | Microsoft Defender for Storage with on-upload malware scanning; security contact email for alerts | DE.CM-09, DE.AE-02 | 8.7 Protection against malware; 8.16 Monitoring activities | Denise Coleman | 2 | 0 |  | 210 |  | 2 | 4 | 1 | O1, O3 | Files arrive from many clinical devices; scanning stops malware spreading through shared storage.
C07 | Conditional Access and phishing-resistant MFA | Mitigate | R12 | Entra ID P1 for 31 users; Conditional Access requiring phishing-resistant methods (passkeys in Microsoft Authenticator) for clinical and admin groups; sign-in risk blocking | PR.AA-03, PR.AA-05 | 8.5 Secure authentication; 5.17 Authentication information | Sabitha S Karanavar | 16 | 0 |  | 2232 |  | 3 | 6 | 3 | O1, O2, O3 | Security defaults allow push/OTP MFA that AiTM kits can proxy; passkeys are bound to the real sign-in site.
C08 | Tenant hardening | Mitigate | R08 | Disable user app registration and tenant creation; restrict guest invites to admins; admin consent workflow | PR.AA-05, PR.PS-01 | 5.15 Access control; 8.9 Configuration management | Sabitha S Karanavar | 4 | 0 |  | 0 |  | 1 | 1 | 1 | O2, O3 | Three insecure defaults found by the checklist; fixing them costs only configuration time.
C09 | EHR access auditing and owner review | Mitigate | R13 | Record-level EHR access logging; monthly review of unusual access by the system owner; reason-code prompt for out-of-unit records | DE.CM-03, PR.AA-05 | 8.15 Logging; 5.18 Access rights | Denise Coleman | 8 | 0 |  | 3600 |  | 3 | 6 | 3 | O2, O3 | Snooping is the most common OCR complaint; visible auditing deters it and finds it early.
C10 | Sanction policy and training tracking | Mitigate | R14 | Written workforce sanction policy; annual HIPAA training with completion tracking | PR.AT-01, GV.RR-04 | 6.4 Disciplinary process; 6.3 Information security awareness, education and training | Daniel Osei | 12 | 0 |  | 500 |  | 2 | 3 | 2 | O2 | Required HIPAA standard (§164.308(a)(1)(ii)(C)) and an easy audit finding to close.
C11 | Privacy Officer and breach procedure | Mitigate | R16 | Designate a Privacy Officer; documented breach-risk assessment and 60-day notification procedure; annual breach tabletop | GV.RR-02, RS.CO-02 | 5.2 Roles and responsibilities; 5.24 Incident management planning; 5.34 Privacy and protection of PII | Denise Coleman | 16 | 0 |  | 5000 |  | 3 | 5 | 3 | O2, O3 | HIPAA requires the role; a clear owner stops the §164.404 deadline being missed.
C12 | Contractor lifecycle and BAA | Transfer | R06 | Business Associate Agreement with indemnification and proof of the contractor firm's cyber insurance; account end date and quarterly review | GV.SC-05, PR.AA-01 | 5.19 Supplier relationships; 5.20 Supplier agreements; 5.18 Access rights | Kevin O'Brien | 6 | 1500 |  | 0 |  | 1 | 1 | 2 | O2, O4 | Transfers liability for contractor-caused breaches to the contractor firm and its insurer; expiry limits exposure time.
C13 | Decommission legacy public server | Avoid | R09, R10 | Remove the 2014-era SSH/Apache host from service and from DNS; migrate any needed content to a supported, patched platform | ID.AM-08, PR.PS-02 | 8.8 Management of technical vulnerabilities; 5.9 Inventory of information assets | Kevin O'Brien | 4 | 0 |  | 0 |  | 1 | 2 | 1 | O3, O4 | The server holds no ePHI and supports no business process; removing it eliminates both CVE risks for less than patching cost.
C14 | Separate test from production | Avoid | R07 | Delete Test Nurse - EHR from the production tenant; run tests in a separate non-production subscription with synthetic data | PR.AA-01, PR.PS-01 | 8.31 Separation of development, test and production environments | Sabitha S Karanavar | 4 | 0 |  | 0 |  | 1 | 1 | 1 | O2 | Eliminates a shared identity with ePHI access instead of trying to control it.
T01 | Cyber liability insurance | Transfer | R02, R05 | Cyber policy with $5M limit and $100K retention covering breach response, notification, regulatory defence and business interruption | GV.RM-04 | 5.19-adjacent (risk financing; outside Annex A) | Brian Adeyemi | 8 | 0 |  | 25000 |  | 3 | 7 | 2 | O4 | Moves the financial tail of residual breach and ransomware losses to an insurer after controls lower the premium.
A01 | Formal acceptance — accidental deletion | Accept | R15 | Accept: weighted score 5.8 (Low) is within appetite; two experienced admins; RA-GRS keeps data if resources are rebuilt. Review annually. | GV.RM-02 | Clause 6.1.3 (risk owner acceptance) | Kevin O'Brien | 1 | 0 |  | 0 |  | 1 | 1 | 1 | O4 | Treatment cost would exceed benefit for a Low risk; acceptance is documented with a review trigger.
Total

## Treatment Plan
Risk Treatment Plan — all 16 risks
Every risk has a strategy (Avoid / Mitigate / Transfer / Accept), controls, owner and target
Risk | Title | Risk owner | Strategy | Controls | Inherent score | Inherent rating | Target date | Acceptance of residual by
R01 | Security incident goes undetected for months (no central logging or alerting) | Fatima Ali | Mitigate | C01 | 16.64 | High | Week 4 | System owner + Security & Risk Lead
R02 | ePHI exfiltration from EHR storage over the public internet | Fatima Ali | Mitigate + Transfer | C02, T01 | 11.76 | High | Week 8 | Security Officer (Low)
R03 | Lateral movement from Web tier to Data tier | Fatima Ali | Mitigate | C03 | 13.56 | High | Week 1 | Security Officer (Low)
R04 | Loss or takeover of the only Global Administrator account | Sabitha S Karanavar | Mitigate | C04 | 9.72 | Medium | Week 1 | Security Officer (Low)
R05 | Ransomware or malicious deletion destroys EHR data | Fatima Ali | Mitigate + Transfer | C05, T01 | 14.01 | High | Week 8 | System owner + Security & Risk Lead
R06 | Contractor retains access after engagement ends; no BAA | Kevin O'Brien | Transfer | C12 | 4.6 | Low | Week 2 | Security Officer (Low)
R07 | Shared test account in production can read ePHI | Sabitha S Karanavar | Avoid | C14 | 3.56 | Low | Week 1 | n/a
R08 | Consent phishing or rogue app via open tenant settings | Sabitha S Karanavar | Mitigate | C08 | 8.91 | Medium | Week 1 | Security Officer (Low)
R09 | Remote code execution via OpenSSH 6.6.1p1 (CVE-2023-38408, CVSS 9.8) | Kevin O'Brien | Avoid | C13 | 9.57 | Medium | Week 2 | n/a
R10 | Remote code execution via Apache 2.4.7 mod_lua (CVE-2021-44790, CVSS 9.8) | Kevin O'Brien | Avoid | C13 | 12.76 | High | Week 2 | n/a
R11 | Malware uploaded to EHR storage is not detected | Denise Coleman | Mitigate | C06 | 10.08 | Medium | Week 4 | Security Officer (Low)
R12 | Clinician credentials stolen by MFA-bypass (AiTM) phishing | Denise Coleman | Mitigate | C07 | 8.91 | Medium | Week 8 | Security Officer (Low)
R13 | Workforce member views patient records without a care need (snooping) | Denise Coleman | Mitigate | C09 | 7.62 | Medium | Week 8 | Security Officer (Low)
R14 | Workforce violations go unpunished; training not tracked | Daniel Osei | Mitigate | C10 | 3.94 | Low | Week 4 | Security Officer (Low)
R15 | Accidental deletion of production network or storage | Kevin O'Brien | Accept | A01 | 5.82 | Low | Week 1 | Security Officer (Low)
R16 | Breach notification deadline missed (no Privacy Officer) | Denise Coleman | Mitigate | C11 | 6.12 | Medium | Week 7 | Security Officer (Low)

## Cost-Benefit
Cost-Benefit Analysis
ALE before/after from the Risk Assessment ALE model; annualized control cost from Controls sheet
Risk | Control | ALE before | ALE after | ALE reduction | Annualized cost | Net annual benefit | ROSI | Payback (days)
R01 | C01 Central logging, alerting and flow logs | 864926 | 345971
R02 | C02 EHR storage network lockdown | 600643 | 120129
R05 | C05 Ransomware-resilient recovery | 1057132 | 288309
R12 | C07 Conditional Access and phishing-resistant MFA | 168180 | 38441
R13 | C09 EHR access auditing and owner review | 74960 | 24987
Total
Risk transfer — cyber insurance (T01)
Residual ALE R02 + R05 after controls
Share covered above retention (assumption) | 80%
Expected annual recovery
Annual premium (assumption) | 25000
Net expected benefit
Policy limit / retention | $5,000,000 / $100,000

## Residual Risk
Inherent vs Residual Risk and Control Effectiveness
Residual score = residual likelihood × weighted impact (weights in H3:K3). Effectiveness = 1 − residual / inherent. | [6 empty] | w Financial | w Operational | w Compliance | w Reputation
[7 empty] | 19% | 36% | 33% | 12%
Risk | Title | Strategy | Controls | Inherent score | Inherent rating | Residual L | Residual F | Residual O | Residual C | Residual R | Residual score | Residual rating | Effectiveness | Why it drops
R01 | Security incident goes undetected for months (no central logging or alerting) | Mitigate | C01 | 16.64 | High | 2 | 3 | 3 | 4 | 3 |  |  |  | Alerts cut dwell time from months to hours (lower impact) and deter attackers (L 4→2)
R02 | ePHI exfiltration from EHR storage over the public internet | Mitigate + Transfer | C02, T01 | 11.76 | High | 1 | 5 | 2 | 5 | 5 |  |  |  | No internet path to storage; exploitation needs an insider with RBAC (L 3→1)
R03 | Lateral movement from Web tier to Data tier | Mitigate | C03 | 13.56 | High | 1 | 5 | 4 | 5 | 4 |  |  |  | Deny rule leaves only SQL 1433 from the App tier (L 3→1)
R04 | Loss or takeover of the only Global Administrator account | Mitigate | C04 | 9.72 | Medium | 1 | 3 | 4 | 3 | 2 |  |  |  | Break-glass and second admin remove lockout; PIM removes standing privilege (L 3→1)
R05 | Ransomware or malicious deletion destroys EHR data | Mitigate + Transfer | C05, T01 | 14.01 | High | 3 | 3 | 3 | 3 | 3 |  |  |  | Attacks still likely, but versioned, immutable backups cap outage within MTD (impact 5→3)
R06 | Contractor retains access after engagement ends; no BAA | Transfer | C12 | 4.6 | Low | 1 | 2 | 1 | 3 | 2 |  |  |  | Expiry limits exposure; BAA moves liability to contractor firm (L 2→1, C 4→3)
R07 | Shared test account in production can read ePHI | Avoid | C14 | 3.56 | Low | 0 | 0 | 0 | 0 | 0 | 0 | Eliminated |  | Account removed — risk eliminated
R08 | Consent phishing or rogue app via open tenant settings | Mitigate | C08 | 8.91 | Medium | 1 | 3 | 2 | 4 | 3 |  |  |  | Users can no longer register or consent to apps (L 3→1)
R09 | Remote code execution via OpenSSH 6.6.1p1 (CVE-2023-38408, CVSS 9.8) | Avoid | C13 | 9.57 | Medium | 0 | 0 | 0 | 0 | 0 | 0 | Eliminated |  | Server decommissioned — risk eliminated
R10 | Remote code execution via Apache 2.4.7 mod_lua (CVE-2021-44790, CVSS 9.8) | Avoid | C13 | 12.76 | High | 0 | 0 | 0 | 0 | 0 | 0 | Eliminated |  | Server decommissioned — risk eliminated
R11 | Malware uploaded to EHR storage is not detected | Mitigate | C06 | 10.08 | Medium | 2 | 3 | 2 | 3 | 3 |  |  |  | Uploads scanned before use (L 3→2, O 4→2)
R12 | Clinician credentials stolen by MFA-bypass (AiTM) phishing | Mitigate | C07 | 8.91 | Medium | 1 | 3 | 2 | 4 | 3 |  |  |  | Phishing-resistant MFA defeats AiTM proxies (L 3→1)
R13 | Workforce member views patient records without a care need (snooping) | Mitigate | C09 | 7.62 | Medium | 2 | 2 | 1 | 4 | 3 |  |  |  | Auditing deters and detects early (L 3→2, R 4→3); some snooping remains — residual accepted by owner
R14 | Workforce violations go unpunished; training not tracked | Mitigate | C10 | 3.94 | Low | 1 | 2 | 1 | 3 | 2 |  |  |  | Policy and tracked training in place (L 2→1)
R15 | Accidental deletion of production network or storage | Accept | A01 | 5.82 | Low | 2 | 3 | 4 | 2 | 2 |  |  |  | Accepted — no change
R16 | Breach notification deadline missed (no Privacy Officer) | Mitigate | C11 | 6.12 | Medium | 1 | 3 | 1 | 4 | 4 |  |  |  | Named Privacy Officer and procedure (L 2→1, C 5→4)
Total / portfolio effectiveness

## KPIs & Monitoring
Control Effectiveness Measures and Monitoring
Status column is filled in at each review; Red items escalate per the HVMC escalation matrix
Control | Name | Owner | KPI (metric) | Target | Data source / test | Frequency | Status (G/A/R) | Last checked | Notes
C01 | Central logging, alerting and flow logs | Fatima Ali | Resources sending logs / alert-to-triage time | 100% / < 15 min | az monitor diagnostic-settings list; test alert | Monthly
C02 | EHR storage network lockdown | Fatima Ali | publicNetworkAccess / allowSharedKeyAccess | Disabled / false | az storage account show | Monthly
C03 | Enforced network segmentation | Fatima Ali | Web→Data test on non-1433 port / Policy compliance | Blocked / 100% | Quarterly connectivity test; Azure Policy | Quarterly
C04 | Privileged access resilience | Sabitha S Karanavar | Standing Global Admins / break-glass alert test | ≤ 2 + break-glass / pass | Entra roles report; quarterly test sign-in | Quarterly
C05 | Ransomware-resilient recovery | Fatima Ali | Restore test result vs RTO/RPO | ≤ 4 h / ≤ 15 min | Quarterly restore drill record | Quarterly
C06 | Malware scanning for EHR uploads | Denise Coleman | Scan coverage / alerts reviewed in SLA | 100% / 100% | Defender for Cloud | Monthly
C07 | Conditional Access and phishing-resistant MFA | Sabitha S Karanavar | Users covered by CA / phishing-resistant registration | 100% / ≥ 90% | Entra authentication-methods report | Monthly
C08 | Tenant hardening | Sabitha S Karanavar | authorizationPolicy settings | allowedToCreateApps=false; invites=admins | Graph authorizationPolicy | Monthly
C09 | EHR access auditing and owner review | Denise Coleman | Monthly reviews completed / unexplained accesses | 100% / 0 open > 30 days | Review log | Monthly
C10 | Sanction policy and training tracking | Daniel Osei | Training completion | ≥ 95% annually | HR training records | Quarterly
C11 | Privacy Officer and breach procedure | Denise Coleman | Breach assessments completed within 5 days | 100% | Incident records; tabletop report | Annually + per incident
C12 | Contractor lifecycle and BAA | Kevin O'Brien | Contractor accounts with end date / BAA on file | 100% / yes | Entra user report; contract register | Quarterly
C13 | Decommission legacy public server | Kevin O'Brien | Internet scan of former host | 0 open ports | nmap from outside | Once, then quarterly
C14 | Separate test from production | Sabitha S Karanavar | Test/shared accounts in production | 0 | Entra user list | Monthly
T01 | Cyber liability insurance | Brian Adeyemi | Policy in force / coverage vs residual ALE | Yes / ≥ 100% | Insurance certificate | Annually
A01 | Formal acceptance — accidental deletion | Kevin O'Brien | Number of admins / incidents | ≤ 4 / 0 | Entra roles; incident log | Annually

## Timeline
Implementation Timeline (week 1 = Oct 19, 2026)
Bars are formulas: a cell fills when the week falls inside start..start+weeks−1
ID | Control | Owner | Phase | Start | Weeks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
C01 | Central logging, alerting and flow logs | Fatima Ali | 2 | 3 | 2
C02 | EHR storage network lockdown | Fatima Ali | 1 | 1 | 1
C03 | Enforced network segmentation | Fatima Ali | 1 | 1 | 1
C04 | Privileged access resilience | Sabitha S Karanavar | 1 | 1 | 1
C05 | Ransomware-resilient recovery | Fatima Ali | 2 | 3 | 3
C06 | Malware scanning for EHR uploads | Denise Coleman | 2 | 4 | 1
C07 | Conditional Access and phishing-resistant MFA | Sabitha S Karanavar | 3 | 6 | 3
C08 | Tenant hardening | Sabitha S Karanavar | 1 | 1 | 1
C09 | EHR access auditing and owner review | Denise Coleman | 3 | 6 | 3
C10 | Sanction policy and training tracking | Daniel Osei | 2 | 3 | 2
C11 | Privacy Officer and breach procedure | Denise Coleman | 3 | 5 | 3
C12 | Contractor lifecycle and BAA | Kevin O'Brien | 1 | 1 | 2
C13 | Decommission legacy public server | Kevin O'Brien | 1 | 2 | 1
C14 | Separate test from production | Sabitha S Karanavar | 1 | 1 | 1
T01 | Cyber liability insurance | Brian Adeyemi | 3 | 7 | 2
A01 | Formal acceptance — accidental deletion | Kevin O'Brien | 1 | 1 | 1

## Business Alignment
Alignment of Controls to HVMC Business Objectives
● = control directly supports the objective
Control | Name | O1: Continuous, safe patient care | O2: HIPAA compliance (avoid OCR penalties) | O3: Protect patient trust and HVMC reputation | O4: Financial sustainability | O5: Secure migration of LIS and Pharmacy to Azure
C01 | Central logging, alerting and flow logs | ● | ● | ●
C02 | EHR storage network lockdown |  | ● | ●
C03 | Enforced network segmentation | ● | ●
C04 | Privileged access resilience | ● | ●
C05 | Ransomware-resilient recovery | ● | ● |  | ●
C06 | Malware scanning for EHR uploads | ● |  | ●
C07 | Conditional Access and phishing-resistant MFA | ● | ● | ●
C08 | Tenant hardening |  | ● | ●
C09 | EHR access auditing and owner review |  | ● | ●
C10 | Sanction policy and training tracking |  | ●
C11 | Privacy Officer and breach procedure |  | ● | ●
C12 | Contractor lifecycle and BAA |  | ● |  | ●
C13 | Decommission legacy public server |  |  | ● | ●
C14 | Separate test from production |  | ●
T01 | Cyber liability insurance |  |  |  | ●
A01 | Formal acceptance — accidental deletion |  |  |  | ●