## sabitha's project board
Sabitha's Project Board
Healthcare IAM Operations Home Lab — 12-Week Daily Task Breakdown (Network Security + Cyber Threats & Vulnerabilities rubrics integrated into Weeks 1-4; UTM/Ubuntu Server + Samba4 AD DC substituted for Windows Server AD DS)
Week 1 — Scope Definition, First Build Steps, and Network Topology/Architecture (Aug 17 – Aug 22)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Define Organization Scenario and Scope |  | Sabitha S Karanavar | Description: Define the fictional hospital's name, confirm 30 employees, list departments and roles, write a one-paragraph project scope statement, and note what's out of scope (no custom app, no real hybrid sync). ¦ Deliverable: One-page scenario write-up + department list. |  | 2026-08-17 |  | Sabitha S Karanavar
Build RBAC Skeleton and Simulated Application List |  | Sabitha S Karanavar | Description: For each department, define its simulated application (shared folder + future Entra app pairing), sketch the OU structure, and decide the security group naming convention. ¦ Deliverable: RBAC matrix v1 (role -> app -> access level) + OU sketch. |  | 2026-08-18 |  | Sabitha S Karanavar
Set Up UTM and Server VM Shell |  | Sabitha S Karanavar | Description: Install UTM on macOS, download the Ubuntu Server ISO, create the Server VM shell, and configure RAM/CPU/disk. ¦ Deliverable: Bootable Server VM (screenshot). |  | 2026-08-19 |  | Sabitha S Karanavar
Install Ubuntu Server OS |  | Sabitha S Karanavar | Description: Install Ubuntu Server, set the hostname, configure a static IP, and verify network connectivity. ¦ Deliverable: Ubuntu Server installed and reachable on the lab network (screenshot). |  | 2026-08-20 |  | Sabitha S Karanavar
[Network Security Rubric] Network Topology Diagram and Report |  | Sabitha S Karanavar | Description: Produce a network topology diagram covering 1 configuration (choose LAN, WAN, MAN, or PAN) for the home lab, and explain how this topology supports secure communication and network management. ¦ Deliverable: Topology diagram + written explanation. (Network Security Rubric — Understand and Implement Network Topologies: Complete) |  | 2026-08-21 |  | Sabitha S Karanavar
[Network Security Rubric] OSI/TCP-IP Model, Subnetting and Secure Architecture Diagram |  | Sabitha S Karanavar | Description: Create a network diagram that includes the OSI model and TCP/IP model mapped to 1 lab device, proper subnetting for 1 subnet, and a secure network architecture showing specific security protocols in use. ¦ Deliverable: Network diagram (OSI + TCP/IP + subnetting + security protocols). (Network Security Rubric — Design Network Protocols and Architectures: Complete) |  | 2026-08-22 |  | Sabitha S Karanavar
Week 1 Status Update |  |  |  |  | 2026-08-22 |  | Sabitha S Karanavar
[5 empty] | 2026-08-17 to 2026-08-22 | 0/6
Week 2 — Samba4 Domain Controller, Client, and Network Security Fundamentals (Aug 24 – Aug 29)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Provision Samba as AD Domain Controller |  | Sabitha S Karanavar | Description: Install samba, krb5-user, and winbind on the Ubuntu Server VM; run samba-tool domain provision --use-rfc2307; point DNS at Samba's internal DNS and disable systemd-resolved's port-53 stub listener; start samba-ad-dc and verify with samba-tool domain info and SRV DNS lookups. ¦ Deliverable: Functioning Samba AD domain controller (samba-tool domain info screenshot). |  | 2026-08-24 |  | Sabitha S Karanavar
Build and Join Client VM |  | Sabitha S Karanavar | Description: Create the Client VM, install the client OS, join it to the Samba domain, and verify domain login. ¦ Deliverable: Domain-joined client (screenshot). |  | 2026-08-25 |  | Sabitha S Karanavar
Build OU Structure |  | Sabitha S Karanavar | Description: Create top-level department OUs and sub-OUs matching the Week 1 design, using samba-tool ou create (or RSAT installed on the joined Windows client, pointed at the Samba domain). ¦ Deliverable: OU hierarchy visible via samba-tool ou list or ADUC (screenshot). |  | 2026-08-26 |  | Sabitha S Karanavar
Create Security Groups + [Network Security Rubric] Implement Network Security Fundamentals |  | Sabitha S Karanavar | Description: Create all security groups per the RBAC matrix using samba-tool group add, following the naming convention. Then implement and document 1 firewall rule, 1 IDS configuration, and 1 IPS configuration on the lab network, with 1 example of a detected event. ¦ Deliverable: Full group list created (screenshot) + firewall/IDS/IPS report with 1 detected-event example. (Network Security Rubric — Implement Network Security Fundamentals: Complete) |  | 2026-08-27 |  | Sabitha S Karanavar
Build On-Prem Apps via Shared Folders + [Network Security Rubric] Implement Access Control Measures |  | Sabitha S Karanavar | Description: Create shared folders for each simulated app and lock down access using Samba share permissions / POSIX ACLs mapped to AD security groups (there's no NTFS on Linux — same AD-group-based access control concept, different filesystem mechanism). Document this as your Access Control evidence: at least 1 Access Control List (ACL) configuration, 1 access control model in use (e.g., DAC via group-based share permissions), and 1 user access level. ¦ Deliverable: Working folder-permission RBAC — screenshot of access difference tested across two roles + access control report. (Network Security Rubric — Implement Access Control Measures: Complete) |  | 2026-08-28 |  | Sabitha S Karanavar
[Network Security Rubric] Secure Wireless Networks |  | Sabitha S Karanavar | Description: Configure WPA2 or WPA3 for 1 wireless network in the lab, and configure a WIPS (Wireless Intrusion Prevention System) to prevent unauthorized access. ¦ Deliverable: Wireless security documentation with WPA2/WPA3 config + WIPS. (Network Security Rubric — Secure Wireless Networks: Complete) |  | 2026-08-29 |  | Sabitha S Karanavar
Week 2 Status Update |  |  |  |  | 2026-08-29 |  | Sabitha S Karanavar
[5 empty] | 2026-08-24 to 2026-08-29 | 0/6
Week 3 — Password Policy, User Accounts, Security Tools, and Threat Analysis (Aug 31 – Sep 5)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Configure Password Policy + Create All 30 Users |  | Sabitha S Karanavar | Description: Set the domain-wide password policy (complexity, minimum length, lockout threshold, expiration) with samba-tool domain passwordsettings set and verify it applied (Samba supports only one domain-wide password policy — no per-OU fine-grained policies/PSOs; editing GPOs otherwise needs RSAT GPMC on a Windows client). Then create all 30 employee accounts, placed in the correct OUs and groups, and verify each account's properties and group memberships. ¦ Deliverable: Password policy confirmation screenshot + full 30-user roster (screenshot of complete directory). |  | 2026-08-31 |  | Sabitha S Karanavar
[Network Security Rubric] Utilize Network Security Tools — Wireshark |  | Sabitha S Karanavar | Description: Capture live traffic on the lab network with Wireshark and write up an analysis of what the capture shows. ¦ Deliverable: 1 Wireshark capture + written analysis (1st of 3 required tool outputs for the Security Tools rubric item). |  | 2026-09-01 |  | Sabitha S Karanavar
[Network Security Rubric] Security Tools — Vulnerability Scanner + [Cyber Threats Rubric] Apply Vulnerability Assessment Techniques |  | Sabitha S Karanavar | Description: Run 1 network vulnerability scan using Nmap or OpenVAS, documenting scan configuration, summary of findings, and vulnerability classification. In the same session, run 1 asset discovery scan documenting discovered systems and services, critical asset identification, and basic network mapping. Document methodology and potential security implications for both — this single scanning session satisfies both rubrics' scanning requirements. ¦ Deliverable: Vulnerability scanner report + asset discovery report. (Network Security Rubric — Security Tools [2nd of 3 outputs]; Cyber Threats Rubric — Apply Vulnerability Assessment Techniques: Complete) |  | 2026-09-02 |  | Sabitha S Karanavar
[Network Security Rubric] Security Tools — Pentest Output + Monitor and Respond to Security Events |  | Sabitha S Karanavar | Description: Run 1 network penetration testing tool against the lab and capture its output — this generates the security event you'll monitor and respond to. Document the security incident identified, the steps taken for incident response, and support it with logs and screenshots. ¦ Deliverable: Pentest tool output (3rd/3rd Security Tools output — Network Security Rubric — Utilize Network Security Tools: Complete) + incident response report with logs/screenshots (Network Security Rubric — Monitor and Respond to Network Security Events: Complete). This incident is reused/extended for Week 4's Security Monitoring & IR deliverable. |  | 2026-09-03 |  | Sabitha S Karanavar
[Cyber Threats Rubric] Identify and Analyze Cyber Threats — Phishing Template |  | Sabitha S Karanavar | Description: Deploy a Kali or Parrot OS VM, then build 1 phishing template using the Social-Engineering Toolkit (SET). ¦ Deliverable: Kali/Parrot VM running + SET phishing template (screenshot/export) (1st of 3 parts of Identify and Analyze Cyber Threats). |  | 2026-09-04 |  | Sabitha S Karanavar
[Cyber Threats Rubric] Identify and Analyze Cyber Threats — Malware Analysis + APT/MITRE Mapping |  | Sabitha S Karanavar | Description: Analyze a malware sample using VirusTotal or Any.Run/Hybrid Analysis, documenting detection results, behavioral indicators, and potential impact. Then map 1 real APT campaign to the MITRE ATT&CK framework. ¦ Deliverable: Malware analysis write-up + APT-to-MITRE-ATT&CK mapping. (Cyber Threats Rubric — Identify and Analyze Cyber Threats: Complete) |  | 2026-09-05 |  | Sabitha S Karanavar
Week 3 Status Update |  |  |  |  | 2026-09-05 |  | Sabitha S Karanavar
[5 empty] | 2026-08-31 to 2026-09-05 | 0/6
Week 4 — Entra ID Foundation, Threat Intelligence, and Risk Management (Sep 7 – Sep 12)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Create Entra ID Tenant |  | Sabitha S Karanavar | Description: Stand up the Microsoft Entra ID tenant and note that real hybrid sync (Entra Connect) is out of scope for this lab. ¦ Deliverable: Active Entra tenant. |  | 2026-09-07 |  | Sabitha S Karanavar
Create Cloud Users and Groups |  | Sabitha S Karanavar | Description: Create cloud users mirroring on-prem AD (bulk CSV import for PowerShell practice), plus mirrored cloud groups. ¦ Deliverable: 30 cloud users + groups, screenshot of Entra ID user list. |  | 2026-09-08 |  | Sabitha S Karanavar
Build Simulated Enterprise Apps in Entra ID + Enable and Configure MFA |  | Sabitha S Karanavar | Description: Create custom Enterprise Application objects and assign cloud groups to them. Then enable MFA in Entra ID, configure Microsoft Authenticator as the method, and enroll at least one privileged account. ¦ Deliverable: App-to-group assignments visible in Entra ID (screenshot) + MFA policy active (screenshot). |  | 2026-09-09 |  | Sabitha S Karanavar
[Cyber Threats Rubric] Implement Threat Intelligence Principles — IoCs + OpenCTI Setup |  | Sabitha S Karanavar | Description: Analyze 2 Indicators of Compromise (IoCs), documenting detection methods used and how each indicates a threat. Stand up the OpenCTI Threat Intelligence Platform via Docker or system installation. ¦ Deliverable: 2-IoC analysis write-up + OpenCTI platform running (setup screenshot). |  | 2026-09-10 |  | Sabitha S Karanavar
[Cyber Threats Rubric] Implement Threat Intelligence Principles — Connectors + Usage Demo |  | Sabitha S Karanavar | Description: Configure at least 2 connectors in OpenCTI, document the platform setup and connector integration, and demonstrate basic usage. ¦ Deliverable: 2 connectors configured + usage demonstration (screenshots). (Cyber Threats Rubric — Implement Threat Intelligence Principles: Complete) |  | 2026-09-11 |  | Sabitha S Karanavar
[Cyber Threats Rubric] Risk Management + Security Monitoring Use Case |  | Sabitha S Karanavar | Description: From the Week 3 vulnerability scan results, identify risks including 2 critical risks with explanations, treatment recommendations, and basic mitigation steps; create 1 risk monitoring procedure showing how identified risks will be tracked. Separately, set up basic security monitoring with 1 use case demonstrating detection rules, an alert prioritization process, and response procedures (the Week 3 Day 4 incident classification/response/lessons-learned writeup completes the paired Incident Response requirement). ¦ Deliverable: Risk assessment (2 critical risks + treatment/mitigation) + risk monitoring procedure (Cyber Threats Rubric — Develop and Apply Risk Management Strategies: Complete) + monitoring use case documentation (Cyber Threats Rubric — Implement Security Monitoring and Incident Response: Complete). |  | 2026-09-12 |  | Sabitha S Karanavar
Week 4 Status Update |  |  |  |  | 2026-09-12 |  | Sabitha S Karanavar
[5 empty] | 2026-09-07 to 2026-09-12 | 0/6
Week 5 — First JML Activities: Onboarding and Transfer (Sep 14 – Sep 17)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Verify End-to-End Access |  | Sabitha S Karanavar | Description: Test a full login flow for a regular user (domain login -> app access via group assignment) and troubleshoot any gaps. ¦ Deliverable: Confirmed working access chain for at least one role. |  | 2026-09-14 |  | Sabitha S Karanavar
Activity 1 — Employee Onboarding |  | Sabitha S Karanavar | Description: Run a full onboarding scenario for a new nurse hire: create the AD account, assign groups, and provision cloud/app access. ¦ Deliverable: Onboarding executed and screenshotted. |  | 2026-09-15 |  | Sabitha S Karanavar
Document Onboarding Ticket |  | Sabitha S Karanavar | Description: Write up the onboarding scenario as a completed IAM ticket using the template. ¦ Deliverable: Completed onboarding ticket + screenshots. |  | 2026-09-16 |  | Sabitha S Karanavar
Activity 2 — Employee Transfer |  | Sabitha S Karanavar | Description: Simulate a department transfer (e.g., Emergency -> ICU): remove old access, grant new access. ¦ Deliverable: Transfer executed in AD/Entra (screenshot). |  | 2026-09-17 |  | Sabitha S Karanavar
Week 5 Status Update |  |  |  |  | 2026-09-17 |  | Sabitha S Karanavar
[5 empty] | 2026-09-14 to 2026-09-17 | 0/4
Week 6 — Termination and MFA Support (Sep 21 – Sep 24)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Document Transfer Ticket + Retro |  | Sabitha S Karanavar | Description: Write the transfer ticket, then spend 15 minutes noting any gaps from Activities 1-2. ¦ Deliverable: Transfer ticket + short notes. |  | 2026-09-21 |  | Sabitha S Karanavar
Activity 3 — Employee Termination |  | Sabitha S Karanavar | Description: Simulate a contractor termination: disable the account, strip group memberships, and remove app access. ¦ Deliverable: Terminated account fully deprovisioned (before/after screenshot). |  | 2026-09-22 |  | Sabitha S Karanavar
Document Termination Ticket |  | Sabitha S Karanavar | Description: Write the termination ticket with resolution notes. ¦ Deliverable: Completed termination ticket. |  | 2026-09-23 |  | Sabitha S Karanavar
Activity 4 — MFA Support |  | Sabitha S Karanavar | Description: Simulate a doctor losing their MFA device: verify identity per policy, reset MFA, and re-enroll a new device. ¦ Deliverable: MFA reset completed + screenshot. |  | 2026-09-24 |  | Sabitha S Karanavar
Week 6 Status Update |  |  |  |  | 2026-09-24 |  | Sabitha S Karanavar
[5 empty] | 2026-09-21 to 2026-09-24 | 0/4
Week 7 — Access Review (Sep 28 – Oct 1)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Document MFA Ticket |  | Sabitha S Karanavar | Description: Write the MFA support ticket. ¦ Deliverable: Completed MFA ticket. |  | 2026-09-28 |  | Sabitha S Karanavar
Plant Access Review Findings |  | Sabitha S Karanavar | Description: Deliberately create 2-3 realistic issues (a stale/terminated account not fully removed, an over-permissioned group membership) to make the access review realistic. ¦ Deliverable: Issues planted and noted privately (not yet "found"). |  | 2026-09-29 |  | Sabitha S Karanavar
Activity 5 — Access Review |  | Sabitha S Karanavar | Description: Pull current access assignments against the RBAC baseline, identify the planted issues plus any real ones, and compile findings. ¦ Deliverable: Findings list. |  | 2026-09-30 |  | Sabitha S Karanavar
Write Access Review Report + Remediate |  | Sabitha S Karanavar | Description: Write a short findings + corrective-actions report, then fix everything found the same day. ¦ Deliverable: Access review report v1 + environment restored to baseline (before/after screenshot). |  | 2026-10-01 |  | Sabitha S Karanavar
Week 7 Status Update |  |  |  |  | 2026-10-01 |  | Sabitha S Karanavar
[5 empty] | 2026-09-28 to 2026-10-01 | 0/4
Week 8 — Directory Automation (Bash/samba-tool + PowerShell over LDAP) (Oct 5 – Oct 8)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Automation: Query Scripts |  | Sabitha S Karanavar | Description: Write a script (Bash using samba-tool user list / samba-tool group listmembers, or PowerShell 7 driving raw LDAP via System.DirectoryServices) to pull a user/group report — Samba has no Active Directory Web Services, so Get-ADUser/Get-ADGroupMember will not work against it. ¦ Deliverable: Working script + sample output. |  | 2026-10-05 |  | Sabitha S Karanavar
Automation: Automate Account Creation |  | Sabitha S Karanavar | Description: Script the account-creation steps from Activity 1 (samba-tool user create, then samba-tool group addmembers) in Bash or PowerShell 7 over LDAP. ¦ Deliverable: Script that creates a new user end-to-end from one command. |  | 2026-10-06 |  | Sabitha S Karanavar
Automation: Automate Deprovisioning |  | Sabitha S Karanavar | Description: Script the termination steps from Activity 3 (samba-tool user disable, then samba-tool group removemembers). ¦ Deliverable: One-command deprovisioning script. |  | 2026-10-07 |  | Sabitha S Karanavar
Add Security, Reception, Contractor Roles |  | Sabitha S Karanavar | Description: Build OUs, groups, and simulated app access for the three roles not yet built. ¦ Deliverable: RBAC matrix updated and fully built out for all 10 roles. |  | 2026-10-08 |  | Sabitha S Karanavar
Week 8 Status Update |  |  |  |  | 2026-10-08 |  | Sabitha S Karanavar
[5 empty] | 2026-10-05 to 2026-10-08 | 0/4
Week 9 — Expand and Repeat the Lifecycle (Oct 12 – Oct 15)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Contractor Auto-Expiration |  | Sabitha S Karanavar | Description: Set an expiration date on contractor accounts using samba-tool user setexpiry to enforce a 90-day rule (Set-ADAccountExpiration depends on Active Directory Web Services, which Samba does not implement). ¦ Deliverable: Contractor accounts with expiration dates set (screenshot). |  | 2026-10-12 |  | Sabitha S Karanavar
Second Onboarding (Automated) |  | Sabitha S Karanavar | Description: Run a second onboarding scenario using the new automation script, for one of the new roles. ¦ Deliverable: Proof the process is repeatable and automatable. |  | 2026-10-13 |  | Sabitha S Karanavar
Second Transfer/Termination |  | Sabitha S Karanavar | Description: Run one more transfer and one more termination using a new role, to prove repeatability beyond the first pass. ¦ Deliverable: Executed and screenshotted. |  | 2026-10-14 |  | Sabitha S Karanavar
Conditional Access Policy |  | Sabitha S Karanavar | Description: Configure a basic Conditional Access policy in Entra ID (e.g., require MFA for admin/privileged roles). ¦ Deliverable: Policy active (screenshot). |  | 2026-10-15 |  | Sabitha S Karanavar
Week 9 Status Update |  |  |  |  | 2026-10-15 |  | Sabitha S Karanavar
[5 empty] | 2026-10-12 to 2026-10-15 | 0/4
Week 10 — Second Review Cycle and SOPs (Oct 19 – Oct 22)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Second Access Review |  | Sabitha S Karanavar | Description: Re-run the access review process and compare against Week 7 findings. ¦ Deliverable: Second findings list (should be shorter/cleaner). |  | 2026-10-19 |  | Sabitha S Karanavar
Update User Access Matrix |  | Sabitha S Karanavar | Description: Finalize the User Access Matrix to reflect the current, fully-built state of the environment. ¦ Deliverable: Final User Access Matrix. |  | 2026-10-20 |  | Sabitha S Karanavar
Draft All 4 SOPs |  | Sabitha S Karanavar | Description: Write bullet-point SOPs (not essays) for: create account, disable account, reset MFA, run access review. ¦ Deliverable: 4 short SOP documents. |  | 2026-10-21 |  | Sabitha S Karanavar
Organize AD/Entra Screenshots |  | Sabitha S Karanavar | Description: Sort all screenshots into labeled folders by category. ¦ Deliverable: Clean screenshot folder structure. |  | 2026-10-22 |  | Sabitha S Karanavar
Week 10 Status Update |  |  |  |  | 2026-10-22 |  | Sabitha S Karanavar
[5 empty] | 2026-10-19 to 2026-10-22 | 0/4
Week 11 — Evidence and Documentation Reconciliation (Oct 26 – Oct 29)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Organize Ticket/Report Evidence |  | Sabitha S Karanavar | Description: Sort ticket and report screenshots into a portfolio folder structure. ¦ Deliverable: Portfolio-ready evidence folder. |  | 2026-10-26 |  | Sabitha S Karanavar
Reconcile the Design Document |  | Sabitha S Karanavar | Description: Update the design doc to match reality: fix the employee count everywhere, complete the RBAC table for all 10 roles, sync SDLC week labels, remove leftover template header/footer, and fold in the UTM/Ubuntu Server + Samba4 AD DC substitution (in place of VirtualBox/Windows Server AD DS) and the samba-tool/LDAP scripting substitution (in place of PowerShell ADWS cmdlets) so the design doc matches the actual build. ¦ Deliverable: Design doc v2, fully consistent with the build. |  | 2026-10-27 |  | Sabitha S Karanavar
Resume and LinkedIn Summaries |  | Sabitha S Karanavar | Description: Write 3-4 resume bullets and a LinkedIn project summary highlighting the JML lifecycle, RBAC design, PowerShell/Bash automation, and the Network Security + Cyber Threats & Vulnerabilities lab work. ¦ Deliverable: Resume bullets + LinkedIn post draft. |  | 2026-10-28 |  | Sabitha S Karanavar
Interview Talking Points |  | Sabitha S Karanavar | Description: Prepare a walkthrough: RBAC design decisions, each JML activity, the access review findings, what was automated, and the network security / threat-intel work from Weeks 1-4. ¦ Deliverable: Talking points doc. |  | 2026-10-29 |  | Sabitha S Karanavar
Week 11 Status Update |  |  |  |  | 2026-10-29 |  | Sabitha S Karanavar
[5 empty] | 2026-10-26 to 2026-10-29 | 0/4
Week 12 — Publish and Close (Nov 2 – Nov 5)
Name | Subitems | Person | Text | Status | Date | Checkbox | People | Item ID (auto generated)
Final Proofread |  | Sabitha S Karanavar | Description: Final pass on the design doc and portfolio. ¦ Deliverable: Polished, publish-ready doc. |  | 2026-11-02 |  | Sabitha S Karanavar
Publish Portfolio |  | Sabitha S Karanavar | Description: Publish the portfolio (GitHub/portfolio site) and verify all links work. ¦ Deliverable: Published portfolio. |  | 2026-11-03 |  | Sabitha S Karanavar
Rubric Cross-Check |  | Sabitha S Karanavar | Description: Go through course rubric items — including the Network Security and Cyber Threats & Vulnerabilities rubrics completed in Weeks 1-4 — and tag where each is already satisfied by the build. ¦ Deliverable: Rubric mapping notes. |  | 2026-11-04 |  | Sabitha S Karanavar
Final Review and Closure |  | Sabitha S Karanavar | Description: Check everything against the evaluation criteria from the design doc. Confirm nothing's missing. ¦ Deliverable: Project marked complete. |  | 2026-11-05 |  | Sabitha S Karanavar
Week 12 Status Update |  |  |  |  | 2026-11-05 |  | Sabitha S Karanavar
[5 empty] | 2026-11-02 to 2026-11-05 | 0/4